## Read me
Action log
The Project Control Hub · free template
What it is | Minutes that end in an owner and a date. Every action has a person, a due date, what done looks like, and a record of who closed it and on what evidence.
How to use it | 1. One action per row, written as a verb: "Ahmet to issue the wayleave letter by 14 March".
2. Owner is a person, never a department.
3. "What done looks like" decides whether it can ever be closed.
4. Close it with a name, a date and the evidence. Then count what you cannot categorise.
Cells | Yellow cells with blue text are yours to fill in.
White cells with black text are formulas. Leave them alone and they keep working.
Explained in | Reporting Topic 23 · Minutes, actions and closure
Risk Topic 13 · Response strategies
This file | Example: actions from one weekly meeting of the example project, taken from the risk responses.
Quantities, durations and dates in this example are illustrative. The events, owners and figures named in the lessons (the rock, the rebar gang, the wayleave letter, the boreholes) are the example project’s.
Use | Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Actions
Action log
Example project · actions from the weekly meeting
As at | 2026-03-16
No. | Raised in | Action | Owner (a person) | Due | What done looks like | If not done | Status | Overdue? | Closed by | Closed on | Evidence of closure
1 | Weekly meeting, 6 Mar | Issue the wayleave letter | Ahmet | 2026-03-14 | Letter sent to the stated address, receipt on file | Deliveries cannot use the access road | Open | Overdue
2 | Weekly meeting, 6 Mar | Drill two boreholes in the north half | Engineer | 2026-03-20 | Two logs filed against the pile layout | Piling continues on assumed ground | Open
3 | Weekly meeting, 6 Mar | Run a credit check on the steel supplier | Buyer | 2026-03-13 | Report on file and read |  | Closed |  | Buyer | 2026-03-12 | Report filed in the supplier folder
4 | Weekly meeting, 6 Mar | Confirm the switchgear lead time in writing | Buyer | 2026-03-18 | Supplier’s written date on file |  | Open
5 | Weekly meeting, 6 Mar | Send the pre-application enquiry for the discharge consent | Engineer | 2026-03-20 | Enquiry acknowledged by the authority |  | Open
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
| Open | 4
| Closed | 1
| Overdue | 1
| Can’t tell (no status) | 0
| Closed with no evidence | 0
The third and fifth numbers are the ones that matter: an action nobody can categorise was never really an action.

## Decisions
Decision log
What was decided, by whom, and on what record
Date | Decision | Decided by | Recorded in | Replaces | Note
2026-03-06 | Treat the boreholes as an investigation response, judged at P80, not on expected value | Project manager | Minutes of the weekly meeting, 6 Mar |  | Risk Topic 13