## Start
Cash flow and S-curve
Profit is an opinion about the end of the job. Cash is a fact about today. This file shows both.
The Project Control Hub · free template
FIVE STEPS
1 | Setup → | The contract terms: value, retention, how long until you are paid, supplier credit, any advance. | 2 minutes
2 | Cash flow → | The cost you pay each month. The engine values the work, holds retention, pays you later. | 10 minutes
3 | Dashboard → | Read the deepest point. That is the cash this job must have access to at its worst. | —
4 | What if → | Test one lever at a time: faster payment, supplier credit, an advance. The profit never moves. | 5 minutes
5 | Portfolio → | Add the other jobs you are running or bidding. The holes stack; check them against the facility. | 5 minutes
HOW THE MONEY MOVES
| You do the work | And pay for it in the month, unless suppliers give you credit.
| It is valued and certified | Retention is carved off every certificate; an advance is recovered from it.
| You are paid, later | Usually a month after the work. Until then, you are financing the client.
| Retention comes back last | Half at completion, half after the defects period. Money earned, held elsewhere.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Red | Cash below zero; the deepest month is darker. Or a facility that is too small.
| Green | Profit, and levers that make the hole shallower.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, a paragraph in plain English, four charts and the five levers.
| Setup | Contract value, retention, payment and supplier timing, advance, overdraft.
| Cash flow | The monthly engine: value, retention, certificates, money in and out, cash position.
| What if | The same job on different terms, side by side with the base.
| Portfolio | Up to five jobs at once, stacked against the overdraft facility.
EXPLAINED IN
Cost & Cash Topic 16 · Cash flow fundamentals
Cost & Cash Topic 17 · The interim payment cycle
Cost & Cash Topic 18 · Overtrading
Cost & Cash Topic 19 · Managing the hole
Blank: twenty-four months ready to fill. The example file shows the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Cash flow |  |  |  |  | The Project Control Hub
DEEPEST CASH POSITION | MONTHS BELOW ZERO | COST OF THE HOLE | PROFIT AT THE END | RETENTION STILL HELD |  | FACILITY HEADROOM
THE CURVE OUT, THE CURVE BACK, AND THE GAP
MOVE THE TIMING, NOT THE PROFIT
FIVE TIMING LEVERS · none of them changes the profit
Lever |  | Effect on the hole | Where to try it | What it costs you
Front-load the schedule of values |  | Shallower | Valuation override | A sceptical client QS
Certify and get paid faster |  | Shallower | What if: payment months | Immaculate applications
Pay your own suppliers later |  | Shallower | What if: supplier credit | A negotiation
Take a mobilisation advance |  | Much shallower | What if: advance % | A bank guarantee; recovery later
Buy materials early / let retention build |  | Deeper | Cost timing; retention % | Cash spent before it is needed
Everything on this page reads from Setup, Cash flow, What if and Portfolio.

## Setup
Setup |  | The Project Control Hub
The contract terms that decide when money moves. None of them change the profit.
Change a term here and watch the Dashboard: the depth of the hole is a timing decision.
Project
Contract value ($) |  | Topic 16: $1,000,000.
Retention held on each certificate | 5% | Usually 5%. Topic 17.
Months from doing the work to being paid | 1 | Value, certify, pay: usually one month, sometimes two.
Months of credit from suppliers | 0 | 0 = you pay in the month. 1 = 30-day terms or better.
Mobilisation advance (% of contract) | 0% | Paid in month 1. Topic 19: 10% would bury the hole.
Advance recovered from each certificate (%) | 0% | Deducted until the advance is repaid.
First retention release: month |  | Usually practical completion. Empty if outside the 24 months.
First release: share of retention | 50% | Usually half.
Second retention release: month |  | End of the defects period, often a year after completion.
Second release: share of retention | 50% | The other half.
Overdraft interest rate (per year) |  | Topic 16: 8%.
Overdraft facility ($) |  | Topic 18: $150,000.
Month 1 ends on |  | Optional. Dates the months.

## Cash flow
Cash flow | [18 empty] | The Project Control Hub
Money out and money in, month by month. The gap between them is the cash this job needs.
Fill the cost you pay each month (column C). Override a valuation (D) only if your schedule of values is front-loaded.
Month | Month end | Cost incurred ($) | Valuation override ($) | Value of work ($) | Advance recovered ($) | Retention deducted ($) | Net certificate ($) | Certificates paid ($) | Advance received ($) | Retention released ($) | Money in ($) | Money out ($) | Cumulative out ($) | Cumulative in ($) | Cash position ($) | Retention held ($) | Interest this month ($) | Below zero (chart) | Above zero (chart)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
RESULTS
Total cost ($)
Contract value ($)
Profit at the end ($)
Deepest cash position ($)
Month of the deepest point
Months with the cash position below zero
Cost of the hole, rule of thumb ($)
Cost of the hole, month by month ($)
Money in by month 24 ($)
Retention still held ($)
Headroom on the overdraft facility ($)
Formulas:
Month end = IF(OR(Setup!$B19="",Setup!$B19=0),"",EOMONTH(Setup!$B19,[Month]-1))

## What if
What if | [21 empty] | The Project Control Hub
The same job with different terms. The profit does not move; the hole does.
Change any yellow term in the right-hand panel (column X). The costs come from the Cash flow sheet.
TERMS FOR THIS SCENARIO
Month | Month end | Cost incurred ($) | Valuation override ($) | Value of work ($) | Advance recovered ($) | Retention deducted ($) | Net certificate ($) | Certificates paid ($) | Advance received ($) | Retention released ($) | Money in ($) | Money out ($) | Cumulative out ($) | Cumulative in ($) | Cash position ($) | Retention held ($) | Interest this month ($) | Below zero (chart) | Above zero (chart) | Each starts equal to Setup. Type over it to test a lever.
1 | [19 empty] | Contract value ($)
2 | [19 empty] | Retention held on each certificate
3 | [19 empty] | Months from doing the work to being paid
4 | [19 empty] | Months of credit from suppliers
5 | [19 empty] | Mobilisation advance (% of contract)
6 | [19 empty] | Advance recovered from each certificate (%)
7 | [19 empty] | First retention release: month
8 | [19 empty] | First release: share of retention
9 | [19 empty] | Second retention release: month
10 | [19 empty] | Second release: share of retention
11 | [19 empty] | Overdraft interest rate (per year)
12 | [19 empty] | Overdraft facility ($)
13 | [19 empty] | Month 1 ends on
14
15
16 | [19 empty] | BASE AGAINST THIS SCENARIO
17 | [20 empty] | Base | Scenario
18 | [19 empty] | Deepest cash position ($)
19 | [19 empty] | Month of the deepest point
20 | [19 empty] | Months below zero
21 | [19 empty] | Cost of the hole, month by month ($)
22 | [19 empty] | Profit at the end ($)
23
24 | [19 empty] | Topic 19 on the same job: front-loading took the hole from -$60,462 to about -$20,462, faster certification to about -$8k, and a 10% advance to a surplus of about $30k. Not one of them earned a dollar more.
RESULTS
Total cost ($)
Contract value ($)
Profit at the end ($)
Deepest cash position ($)
Month of the deepest point
Months with the cash position below zero
Cost of the hole, rule of thumb ($)
Cost of the hole, month by month ($)
Money in by month 24 ($)
Retention still held ($)
Headroom on the overdraft facility ($)
Formulas:
Month end = IF(OR(X19="",X19=0),"",EOMONTH(X19,[Month]-1))

## Portfolio
Portfolio | [7 empty] | The Project Control Hub
Several jobs like this one at once. The holes do not average out; they stack.
Give each job a start month (0 = starts with the first) and a size relative to this one. Compare the total with the facility.
Job | Starts after (months) | Size (× this job) |  | ALL JOBS TOGETHER
Deepest combined position ($)
Month
Overdraft facility ($)
Short of the facility by ($)
Combined profit at the end ($)
Topic 18 stacks three jobs in their cash-hungry months at once: three holes of $60,462 make $181,386. Spread the starts and watch the total. |  |  |  | The profit arrives at the end of each job; the holes arrive together, at the start.
Month | Job A | Job B | Job C | Job D | Job E | All jobs ($) | Facility ($)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36