## Start
Cash flow and S-curve
Profit is an opinion about the end of the job. Cash is a fact about today. This file shows both.
The Project Control Hub · free template · example: the example project
FIVE STEPS
1 | Setup → | The contract terms: value, retention, how long until you are paid, supplier credit, any advance. | 2 minutes
2 | Cash flow → | The cost you pay each month. The engine values the work, holds retention, pays you later. | 10 minutes
3 | Dashboard → | Read the deepest point. That is the cash this job must have access to at its worst. | —
4 | What if → | Test one lever at a time: faster payment, supplier credit, an advance. The profit never moves. | 5 minutes
5 | Portfolio → | Add the other jobs you are running or bidding. The holes stack; check them against the facility. | 5 minutes
HOW THE MONEY MOVES
| You do the work | And pay for it in the month, unless suppliers give you credit.
| It is valued and certified | Retention is carved off every certificate; an advance is recovered from it.
| You are paid, later | Usually a month after the work. Until then, you are financing the client.
| Retention comes back last | Half at completion, half after the defects period. Money earned, held elsewhere.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Red | Cash below zero; the deepest month is darker. Or a facility that is too small.
| Green | Profit, and levers that make the hole shallower.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, a paragraph in plain English, four charts and the five levers.
| Setup | Contract value, retention, payment and supplier timing, advance, overdraft.
| Cash flow | The monthly engine: value, retention, certificates, money in and out, cash position.
| What if | The same job on different terms, side by side with the base.
| Portfolio | Up to five jobs at once, stacked against the overdraft facility.
EXPLAINED IN
Cost & Cash Topic 16 · Cash flow fundamentals
Cost & Cash Topic 17 · The interim payment cycle
Cost & Cash Topic 18 · Overtrading
Cost & Cash Topic 19 · Managing the hole
Example: the example project. Contract $1,000,000, cost $827,008, profit $172,992, 5% retention, paid a month after the work: cash bottoms at -$60,462 in month four and is below zero for eight months; $950,000 comes in and $50,000 is held as retention (Topic 16). Three such jobs at once need $181,386 against a $150,000 facility (Topic 18). The month-by-month cost split is illustrative, chosen so those figures come out the same. The What if sheet tests a 10% advance recovered at 10% a certificate.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Cash flow |  |  |  |  | The Project Control Hub
Example project · contract $1,000,000 · retention 5% · paid 1 month(s) after the work
DEEPEST CASH POSITION | MONTHS BELOW ZERO | COST OF THE HOLE | PROFIT AT THE END | RETENTION STILL HELD |  | FACILITY HEADROOM
-60462.0384 | 8 | 3224.642 | 172992 | 50000 |  | 89537.9616
month 4 | months the job is financed by you | rule of thumb · month by month $2,309 | contract $1,000,000 − cost $827,008 | earned, not yet paid |  | all jobs together: -$181,386
Profit is an opinion; cash is a fact. This job makes $172,992 and still needs $60,462 of cash at its worst, in month 4. It is below zero for 8 months, and $50,000 of earned money is still held as retention at the end.
THE CURVE OUT, THE CURVE BACK, AND THE GAP
MOVE THE TIMING, NOT THE PROFIT
FIVE TIMING LEVERS · none of them changes the profit
Lever |  | Effect on the hole | Where to try it | What it costs you
Front-load the schedule of values |  | Shallower | Valuation override | A sceptical client QS
Certify and get paid faster |  | Shallower | What if: payment months | Immaculate applications
Pay your own suppliers later |  | Shallower | What if: supplier credit | A negotiation
Take a mobilisation advance |  | Much shallower | What if: advance % | A bank guarantee; recovery later
Buy materials early / let retention build |  | Deeper | Cost timing; retention % | Cash spent before it is needed
Everything on this page reads from Setup, Cash flow, What if and Portfolio.

## Setup
Setup |  | The Project Control Hub
The contract terms that decide when money moves. None of them change the profit.
Change a term here and watch the Dashboard: the depth of the hole is a timing decision.
Project | Example project
Contract value ($) | 1000000 | Topic 16: $1,000,000.
Retention held on each certificate | 5% | Usually 5%. Topic 17.
Months from doing the work to being paid | 1 | Value, certify, pay: usually one month, sometimes two.
Months of credit from suppliers | 0 | 0 = you pay in the month. 1 = 30-day terms or better.
Mobilisation advance (% of contract) | 0% | Paid in month 1. Topic 19: 10% would bury the hole.
Advance recovered from each certificate (%) | 0% | Deducted until the advance is repaid.
First retention release: month |  | Usually practical completion. Empty if outside the 24 months.
First release: share of retention | 50% | Usually half.
Second retention release: month |  | End of the defects period, often a year after completion.
Second release: share of retention | 50% | The other half.
Overdraft interest rate (per year) | 8% | Topic 16: 8%.
Overdraft facility ($) | 150000 | Topic 18: $150,000.
Month 1 ends on | 2026-01-31 | Optional. Dates the months.

## Cash flow
Cash flow | [18 empty] | The Project Control Hub
Money out and money in, month by month. The gap between them is the cash this job needs.
Fill the cost you pay each month (column C). Override a valuation (D) only if your schedule of values is front-loaded.
Month | Month end | Cost incurred ($) | Valuation override ($) | Value of work ($) | Advance recovered ($) | Retention deducted ($) | Net certificate ($) | Certificates paid ($) | Advance received ($) | Retention released ($) | Money in ($) | Money out ($) | Cumulative out ($) | Cumulative in ($) | Cash position ($) | Retention held ($) | Interest this month ($) | Below zero (chart) | Above zero (chart)
1 | 2026-01-31 | 19064 |  | 23051.7722 | 0 | 1152.5886 | 21899.1836 | 0 | 0 | 0 | 0 | 19064 | 19064 | 0 | -19064 | 1152.5886 | 127.0933 | -19064 | 0
2 | 2026-02-28 | 45304 |  | 54780.6067 | 0 | 2739.0303 | 52041.5764 | 21899.1836 | 0 | 0 | 21899.1836 | 45304 | 64368 | 21899.1836 | -42468.8164 | 3891.6189 | 283.1254 | -42468.8164 | 0
3 | 2026-03-31 | 64882 |  | 78453.8965 | 0 | 3922.6948 | 74531.2016 | 52041.5764 | 0 | 0 | 52041.5764 | 64882 | 129250 | 73940.7599 | -55309.2401 | 7814.3138 | 368.7283 | -55309.2401 | 0
4 | 2026-04-30 | 79684 |  | 96352.1514 | 0 | 4817.6076 | 91534.5438 | 74531.2016 | 0 | 0 | 74531.2016 | 79684 | 208934 | 148471.9616 | -60462.0384 | 12631.9213 | 403.0803 | -60462.0384 | 0
5 | 2026-05-31 | 89320 |  | 108003.792 | 0 | 5400.1896 | 102603.6024 | 91534.5438 | 0 | 0 | 91534.5438 | 89320 | 298254 | 240006.5054 | -58247.4946 | 18032.1109 | 388.3166 | -58247.4946 | 0
6 | 2026-06-30 | 95403 |  | 115359.2226 | 0 | 5767.9611 | 109591.2615 | 102603.6024 | 0 | 0 | 102603.6024 | 95403 | 393657 | 342610.1078 | -51046.8922 | 23800.0721 | 340.3126 | -51046.8922 | 0
7 | 2026-07-31 | 97010 |  | 117302.3719 | 0 | 5865.1186 | 111437.2533 | 109591.2615 | 0 | 0 | 109591.2615 | 97010 | 490667 | 452201.3693 | -38465.6307 | 29665.1907 | 256.4375 | -38465.6307 | 0
8 | 2026-08-31 | 94250 |  | 113965.0402 | 0 | 5698.252 | 108266.7882 | 111437.2533 | 0 | 0 | 111437.2533 | 94250 | 584917 | 563638.6226 | -21278.3774 | 35363.4427 | 141.8558 | -21278.3774 | 0
9 | 2026-09-30 | 86822 |  | 104983.265 | 0 | 5249.1632 | 99734.1017 | 108266.7882 | 0 | 0 | 108266.7882 | 86822 | 671739 | 671905.4108 | 166.4108 | 40612.6059 | 0 | 0 | 166.4108
10 | 2026-10-31 | 74146 |  | 89655.7228 | 0 | 4482.7861 | 85172.9367 | 99734.1017 | 0 | 0 | 99734.1017 | 74146 | 745885 | 771639.5126 | 25754.5126 | 45095.3921 | 0 | 0 | 25754.5126
11 | 2026-11-30 | 55036 |  | 66548.3284 | 0 | 3327.4164 | 63220.912 | 85172.9367 | 0 | 0 | 85172.9367 | 55036 | 800921 | 856812.4492 | 55891.4492 | 48422.8085 | 0 | 0 | 55891.4492
12 | 2026-12-31 | 26087 |  | 31543.8303 | 0 | 1577.1915 | 29966.6388 | 63220.912 | 0 | 0 | 63220.912 | 26087 | 827008 | 920033.3612 | 93025.3612 | 50000 | 0 | 0 | 93025.3612
13 | 2027-01-31 |  |  | 0 | 0 | 0 | 0 | 29966.6388 | 0 | 0 | 29966.6388 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
14 | 2027-02-28 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
15 | 2027-03-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
16 | 2027-04-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
17 | 2027-05-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
18 | 2027-06-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
19 | 2027-07-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
20 | 2027-08-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
21 | 2027-09-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
22 | 2027-10-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
23 | 2027-11-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
24 | 2027-12-31 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
RESULTS
Total cost ($) |  |  | 827008
Contract value ($) |  |  | 1000000
Profit at the end ($) |  |  | 172992
Deepest cash position ($) |  |  | -60462.0384
Month of the deepest point |  |  | 4
Months with the cash position below zero |  |  | 8
Cost of the hole, rule of thumb ($) |  |  | 3224.642
Cost of the hole, month by month ($) |  |  | 2308.9499
Money in by month 24 ($) |  |  | 950000
Retention still held ($) |  |  | 50000
Headroom on the overdraft facility ($) |  |  | 89537.9616
Formulas:
Month end = IF(OR(Setup!$B19="",Setup!$B19=0),"",EOMONTH(Setup!$B19,[Month]-1))
Note on C7: The lesson gives the totals and the trough. This monthly split is illustrative, chosen so that the cost adds to $827,008 and the cash position bottoms at -$60,462 in month 4, below zero for eight months.
Note on D39: Deepest point × interest rate × months below zero ÷ 12: the rough method in Cost & Cash Topic 16 ($60,000 for eight months at 8% is about $3,225). The next line charges interest only on the actual overdraft each month, which is usually less.

## What if
What if | [21 empty] | The Project Control Hub
The same job with different terms. The profit does not move; the hole does.
Change any yellow term in the right-hand panel (column X). The costs come from the Cash flow sheet.
TERMS FOR THIS SCENARIO
Month | Month end | Cost incurred ($) | Valuation override ($) | Value of work ($) | Advance recovered ($) | Retention deducted ($) | Net certificate ($) | Certificates paid ($) | Advance received ($) | Retention released ($) | Money in ($) | Money out ($) | Cumulative out ($) | Cumulative in ($) | Cash position ($) | Retention held ($) | Interest this month ($) | Below zero (chart) | Above zero (chart) | Each starts equal to Setup. Type over it to test a lever.
1 | 2026-01-31 | 19064 |  | 23051.7722 | 2305.1772 | 1152.5886 | 19594.0063 | 0 | 100000 | 0 | 100000 | 19064 | 19064 | 100000 | 80936 | 1152.5886 | 0 | 0 | 80936 | Contract value ($) | 1000000
2 | 2026-02-28 | 45304 |  | 54780.6067 | 5478.0607 | 2739.0303 | 46563.5157 | 19594.0063 | 0 | 0 | 19594.0063 | 45304 | 64368 | 119594.0063 | 55226.0063 | 3891.6189 | 0 | 0 | 55226.0063 | Retention held on each certificate | 5%
3 | 2026-03-31 | 64882 |  | 78453.8965 | 7845.3896 | 3922.6948 | 66685.812 | 46563.5157 | 0 | 0 | 46563.5157 | 64882 | 129250 | 166157.5221 | 36907.5221 | 7814.3138 | 0 | 0 | 36907.5221 | Months from doing the work to being paid | 1
4 | 2026-04-30 | 79684 |  | 96352.1514 | 9635.2151 | 4817.6076 | 81899.3287 | 66685.812 | 0 | 0 | 66685.812 | 79684 | 208934 | 232843.334 | 23909.334 | 12631.9213 | 0 | 0 | 23909.334 | Months of credit from suppliers | 0
5 | 2026-05-31 | 89320 |  | 108003.792 | 10800.3792 | 5400.1896 | 91803.2232 | 81899.3287 | 0 | 0 | 81899.3287 | 89320 | 298254 | 314742.6627 | 16488.6627 | 18032.1109 | 0 | 0 | 16488.6627 | Mobilisation advance (% of contract) | 10%
6 | 2026-06-30 | 95403 |  | 115359.2226 | 11535.9223 | 5767.9611 | 98055.3392 | 91803.2232 | 0 | 0 | 91803.2232 | 95403 | 393657 | 406545.8859 | 12888.8859 | 23800.0721 | 0 | 0 | 12888.8859 | Advance recovered from each certificate (%) | 10%
7 | 2026-07-31 | 97010 |  | 117302.3719 | 11730.2372 | 5865.1186 | 99707.0161 | 98055.3392 | 0 | 0 | 98055.3392 | 97010 | 490667 | 504601.2251 | 13934.2251 | 29665.1907 | 0 | 0 | 13934.2251 | First retention release: month | 0
8 | 2026-08-31 | 94250 |  | 113965.0402 | 11396.504 | 5698.252 | 96870.2842 | 99707.0161 | 0 | 0 | 99707.0161 | 94250 | 584917 | 604308.2413 | 19391.2413 | 35363.4427 | 0 | 0 | 19391.2413 | First release: share of retention | 50%
9 | 2026-09-30 | 86822 |  | 104983.265 | 10498.3265 | 5249.1632 | 89235.7752 | 96870.2842 | 0 | 0 | 96870.2842 | 86822 | 671739 | 701178.5255 | 29439.5255 | 40612.6059 | 0 | 0 | 29439.5255 | Second retention release: month | 0
10 | 2026-10-31 | 74146 |  | 89655.7228 | 8965.5723 | 4482.7861 | 76207.3644 | 89235.7752 | 0 | 0 | 89235.7752 | 74146 | 745885 | 790414.3007 | 44529.3007 | 45095.3921 | 0 | 0 | 44529.3007 | Second release: share of retention | 50%
11 | 2026-11-30 | 55036 |  | 66548.3284 | 6654.8328 | 3327.4164 | 56566.0792 | 76207.3644 | 0 | 0 | 76207.3644 | 55036 | 800921 | 866621.6651 | 65700.6651 | 48422.8085 | 0 | 0 | 65700.6651 | Overdraft interest rate (per year) | 8%
12 | 2026-12-31 | 26087 |  | 31543.8303 | 3154.383 | 1577.1915 | 26812.2557 | 56566.0792 | 0 | 0 | 56566.0792 | 26087 | 827008 | 923187.7443 | 96179.7443 | 50000 | 0 | 0 | 96179.7443 | Overdraft facility ($) | 150000
13 | 2027-01-31 | 0 |  | 0 | 0 | 0 | 0 | 26812.2557 | 0 | 0 | 26812.2557 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Month 1 ends on | 2026-01-31
14 | 2027-02-28 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
15 | 2027-03-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
16 | 2027-04-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | BASE AGAINST THIS SCENARIO
17 | 2027-05-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 |  | Base | Scenario
18 | 2027-06-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Deepest cash position ($) | -60462.0384 | 12888.8859
19 | 2027-07-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Month of the deepest point | 4
20 | 2027-08-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Months below zero | 8 | 0
21 | 2027-09-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Cost of the hole, month by month ($) | 2308.9499 | 0
22 | 2027-10-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Profit at the end ($) | 172992 | 172992
23 | 2027-11-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992
24 | 2027-12-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827008 | 950000 | 122992 | 50000 | 0 | 0 | 122992 | Topic 19 on the same job: front-loading took the hole from -$60,462 to about -$20,462, faster certification to about -$8k, and a 10% advance to a surplus of about $30k. Not one of them earned a dollar more.
RESULTS
Total cost ($) |  |  | 827008
Contract value ($) |  |  | 1000000
Profit at the end ($) |  |  | 172992
Deepest cash position ($) |  |  | 12888.8859
Month of the deepest point
Months with the cash position below zero |  |  | 0
Cost of the hole, rule of thumb ($) |  |  | 0
Cost of the hole, month by month ($) |  |  | 0
Money in by month 24 ($) |  |  | 950000
Retention still held ($) |  |  | 50000
Headroom on the overdraft facility ($) |  |  | 150000
Formulas:
Month end = IF(OR(X19="",X19=0),"",EOMONTH(X19,[Month]-1))
Note on X11: Example lever: a 10% mobilisation advance ($100,000 in month 1), recovered at 10% of every certificate.
Note on D39: Deepest point × interest rate × months below zero ÷ 12: the rough method in Cost & Cash Topic 16 ($60,000 for eight months at 8% is about $3,225). The next line charges interest only on the actual overdraft each month, which is usually less.

## Portfolio
Portfolio | [7 empty] | The Project Control Hub
Several jobs like this one at once. The holes do not average out; they stack.
Give each job a start month (0 = starts with the first) and a size relative to this one. Compare the total with the facility.
Job | Starts after (months) | Size (× this job) |  | ALL JOBS TOGETHER
Job A | 0 | 1 |  | Deepest combined position ($) |  | -181386.1153
Job B | 0 | 1 |  | Month |  | 4
Job C | 0 | 1 |  | Overdraft facility ($) |  | 150000
|  |  |  | Short of the facility by ($) |  | 31386.1153
|  |  |  | Combined profit at the end ($) |  | 518976
Topic 18 stacks three jobs in their cash-hungry months at once: three holes of $60,462 make $181,386. Spread the starts and watch the total. |  |  |  | The profit arrives at the end of each job; the holes arrive together, at the start.
Month | Job A | Job B | Job C | Job D | Job E | All jobs ($) | Facility ($)
1 | -19064 | -19064 | -19064 | 0 | 0 | -57192 | -150000
2 | -42468.8164 | -42468.8164 | -42468.8164 | 0 | 0 | -127406.4493 | -150000
3 | -55309.2401 | -55309.2401 | -55309.2401 | 0 | 0 | -165927.7202 | -150000
4 | -60462.0384 | -60462.0384 | -60462.0384 | 0 | 0 | -181386.1153 | -150000
5 | -58247.4946 | -58247.4946 | -58247.4946 | 0 | 0 | -174742.4839 | -150000
6 | -51046.8922 | -51046.8922 | -51046.8922 | 0 | 0 | -153140.6767 | -150000
7 | -38465.6307 | -38465.6307 | -38465.6307 | 0 | 0 | -115396.8922 | -150000
8 | -21278.3774 | -21278.3774 | -21278.3774 | 0 | 0 | -63835.1322 | -150000
9 | 166.4108 | 166.4108 | 166.4108 | 0 | 0 | 499.2325 | -150000
10 | 25754.5126 | 25754.5126 | 25754.5126 | 0 | 0 | 77263.5377 | -150000
11 | 55891.4492 | 55891.4492 | 55891.4492 | 0 | 0 | 167674.3476 | -150000
12 | 93025.3612 | 93025.3612 | 93025.3612 | 0 | 0 | 279076.0837 | -150000
13 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
14 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
15 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
16 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
17 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
18 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
19 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
20 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
21 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
22 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
23 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
24 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
25 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
26 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
27 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
28 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
29 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
30 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
31 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
32 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
33 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
34 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
35 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000
36 | 122992 | 122992 | 122992 | 0 | 0 | 368976 | -150000