## 00 Start
Daily site report |  |  |  | The Project Control Hub
The record nobody reads until a claim, an incident or a test result needs it. Make it one that stands.
The Project Control Hub · free template
EVERY DAY, IN FIVE STEPS · type each fact once, in a log; the report and the Dashboard read from there
1 | 03 Day log → | One line for the day: report no., time issued, weather, rainfall, working day, prepared by. | 1 minute
2 | 04 Resource log → | Every crew and every machine, each against its P6 activity ID: number, hours, idle reason. | 5 minutes
3 | 05 Work done log → | The quantity done on each P6 activity, and where it came from: counted, estimated or not yet reported. | 5 minutes
4 | 06 Event log → | Events, instructions and delays; deliveries in the Delivery log, safety in the Safety log. A claim? Notice calendar. | 3 minutes
5 | 01 Daily report → | Pick the date in B5: the report builds itself. Blanks go to Not yet reported, corrections to the Revision log. | 1 minute
COUNTED, OR REMEMBERED?
| Counted | Somebody measured it today: the survey, the store, the attendance sheet.
| Estimated | A foreman’s figure. Allowed, but labelled, and measured later.
| Not yet reported | The day has not finished producing it. A visible blank beats a quiet wrong number.
TWO WAYS TO JUDGE A DAILY REPORT
| Went out on time | Easy to measure, easy to hit, and easy to game by sending an emptier report earlier.
| Never revised after | Cannot be gamed by hurrying. The Dashboard shows both; the second is the one that matters.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in: only in the log sheets, Setup, Contract hours and P6 activities.
| White, black text | A formula. Leave it alone and it keeps working. The Daily report and Dashboard are all formulas.
| Red | Lost day, not reported, overdue, or an event that could become a claim.
WHAT IS IN THIS FILE
READ AND SEND · built for you
| 01 Daily report | A view, not a form: pick a date and it fills itself from the logs. Ready to send.
| 02 Dashboard | The week, picked in C4: six numbers, productivity, four charts, quantities, key events.
EVERY DAY · type the facts
| 03 Day log | One line a day: the header facts. People, plant, events and claims fill themselves.
| 04 Resource log | Every crew and machine against its P6 activity: man-hours and machine-hours.
| 05 Work done log | One line per P6 activity per day: quantities, with their source.
| 06 Event log | Events, instructions, delays and visitors, with the P6 activity affected.
| 07 Delivery log | Every delivery, with delivery note, short or damaged, and its P6 activity.
| 08 Safety log | Incidents, near misses, toolbox talks and inspections.
FOLLOW UP · close the gaps
| 09 Not yet reported | Explicit blanks, followed up until closed.
| 10 Revision log | Every correction, with the old value, the new one and why.
| 11 Notice calendar | Every event that could become a claim, with its notice deadline.
ONCE PER PROJECT · set up
| 12 P6 activities | The Primavera P6 activity list: paste your P6 export here. Every drop-down reads from it.
| 13 Contract hours | Contract quantity and man-hours per P6 activity: the baseline for productivity.
| 14 Setup | The deadline, the notice period and every drop-down list.
| 15 Chart data | Locked calculations behind the Dashboard charts. Nothing to type here.
EXPLAINED IN
Reporting Topic 17 · The daily report
Contract Topic 1 · The notice behind the entitlement
Blank: every log ready to fill, the drop-down lists and the deadline set to usual values. Paste your P6 activity list into 12 P6 activities first. The example file shows ten days of the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## 01 Daily report
Daily site report | [6 empty] | The Project Control Hub
One day, on one page. Every figure says where it came from.
Pick the date in B5. Everything on this page is pulled from the logs: type the facts once, in the Day log, Resource log, Work done log, Delivery log, Event log and Safety log.
Date |  |  |  | Revision |  | raised by each line on the Revision log
Report no. |  |  |  | Due by
Issued at |  |  |  | On time?
Weather, morning |  |  |  | Prepared by
Weather, afternoon |  |  |  | Checked by
Working conditions |  |  |  | Project
Rainfall (mm) |  |  |  | Temp. (°C)
LABOUR
Company | Trade | Headcount | Hours each | Man-hours | P6 Activity ID | Note
Total on site
PLANT
Plant |  | On site | Working | Idle | P6 Activity ID | Hours each | Why idle
| Working | [5 empty] | machine-hours
WORK DONE
P6 Activity ID | Activity | Location | Quantity | Unit | Source | Comment
DELIVERIES
Supplier | Material | Quantity | Unit | Delivery note | Short or damaged? | P6 Activity ID | Note
EVENTS, INSTRUCTIONS, DELAYS, VISITORS
Type | What happened |  |  | P6 Activity ID | Time | Could it become a claim? | Then
HEALTH AND SAFETY
Type | What happened |  |  | Location | Time | Reported to | Action taken
THIS REPORT IN NUMBERS
People on site
Man-hours
Plant working
Plant idle
Quantities counted
Quantities estimated
Not yet reported (on the list)
Events that could become a claim
Deliveries short or damaged
Safety incidents and near misses

## 02 Dashboard
Daily reports | [8 empty] | The Project Control Hub
WEEK | 1
REPORTS ON TIME |  | NEVER REVISED |  | WORKING DAYS LOST |  | AVERAGE ON SITE |  | RAISED, NOT REPORTED |  | POSSIBLE CLAIMS
THE WEEK IN FOUR CHARTS
WHAT THIS WEEK’S REPORTS RECORD · the evidence a claim will ask for later
Date | Working day | People | Revisions | Claims | Key event
WORK DONE THIS WEEK · quantities by P6 activity, from the Work done log
P6 ID | Activity |  | Unit | [7 empty] | Week total
P6 ID | Activity |  | Unit | Quantity this week | Norm (mh / unit) | Earned man-hours | Actual man-hours | Productivity this week | Contract man-hours | % complete | Productivity to date
Week
Nobody reads the daily report until a claim, an incident or a test result needs it. Then it cannot be reconstructed.

## 03 Day log
Day log | [16 empty] | The Project Control Hub
One line per day, so the month can be read at a glance.
Type one line per day here: the header facts only. People, plant, events and not-yet-reported counts fill themselves from the other logs.
Date | Report no. | Issued at | On time? | Revisions | Weather | Working day | People on site | Plant working | Not yet reported | Possible claims | Key event | Weather, morning | Weather, afternoon | Rainfall (mm) | Temp. (°C) | Prepared by | Checked by

## 04 Resource log
Resource log | [10 empty] | The Project Control Hub
One line per resource per P6 activity per day: man-hours and machine-hours, ready to load into P6 as actual units.
Type the facts here, once. One line per crew or machine per P6 activity per day. For plant: Number = working, On site = total on site.
Date | P6 Activity ID | Activity (from P6) | WBS (from P6) | Type | Resource | Company | Number | Hours each | Total hours | On site (plant) | Why idle

## 05 Work done log
Work done log | [7 empty] | The Project Control Hub
One line per P6 activity per day: the quantities the Dashboard adds up by week.
Type the facts here, once: one line per P6 activity per day. The Daily report and the Dashboard read from here.
Date | P6 Activity ID | Activity (from P6) | WBS (from P6) | Location | Quantity | Unit | Source | Comment

## 06 Event log
Event log | [8 empty] | The Project Control Hub
Events, instructions, delays, visitors: one line each. The Daily report and the Notice calendar read from here.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Type | What happened | P6 Activity ID | Activity (from P6) | WBS (from P6) | Time | Could it become a claim? | Then

## 07 Delivery log
Delivery log | [9 empty] | The Project Control Hub
Every delivery that arrives on site, one line each.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Supplier | Material | Quantity | Unit | Delivery note | Short or damaged? | P6 Activity ID | Activity (from P6) | WBS (from P6) | Note

## 08 Safety log
Safety log | [5 empty] | The Project Control Hub
Incidents, near misses, toolbox talks and inspections, one line each.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Type | What happened | Location | Time | Reported to | Action taken

## 09 Not yet reported
Not yet reported | [6 empty] | The Project Control Hub
Fields the day could not close, published as blanks and followed up.
"We will correct it tomorrow" is a promise projects break. A list somebody closes is not.
Report date | Field | Who will supply it | Expected by | Closed on | Closed in revision | Days open | Status

## 10 Revision log
Revision log | [7 empty] | The Project Control Hub
What changed, when, and why. Without it, one day becomes three versions of itself.
One line per correction. The Daily report counts the lines for its date and shows the revision number.
Report date | Report no. | New revision | Field | Old value | New value | Reason | Changed by | Changed on

## 11 Notice calendar
Notice calendar | [9 empty] | The Project Control Hub
Every event that could become a claim, with the date its notice is due.
The contract clock starts on the day of the event, not on the day somebody remembers it.
Event date | Report no. | Event | Notice due by | Notice sent on | Days left | Status | Who sends it | P6 Activity ID | Activity (from P6) | WBS (from P6)

## 12 P6 activities
P6 activities | [14 empty] | The Project Control Hub
The activity IDs the report books work against, from the Primavera P6 programme.
Paste a fresh P6 export (Activity ID, Activity Name, WBS, budgeted quantity, budgeted man-hours) here when the programme is re-baselined. Grey columns calculate themselves from every daily report.
Activity ID | Activity name | WBS | Location | Unit | Budgeted quantity (P6) | Budgeted man-hours (P6) | Quantity to date | Quantity % complete | Remaining quantity | Actual man-hours to date | Man-hours % spent | Earned man-hours | Productivity (earned ÷ actual) | Last reported | Notes
INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND |  | h | [10 empty] | Not loaded to P6 activities; kept for the hours total

## 13 Contract hours
Contract hours | [10 empty] | The Project Control Hub
Contract (budgeted) quantity and man-hours for each P6 activity, and how the job is doing against them.
Blue cells are inputs: take them from the priced bill or the P6 baseline. Everything else fills itself from the Work done log and the Resource log.
Productivity = earned man-hours ÷ actual man-hours. Above 1.00 the gang is beating the contract norm; below 1.00 it is spending more hours than the job was priced for.
P6 Activity ID | Activity | WBS (from P6) | Unit | Contract quantity | Contract man-hours | Norm (man-hours per unit) | Quantity to date | Actual man-hours to date | Earned man-hours to date | % complete | Productivity to date

## 14 Setup
Setup | [10 empty] | The Project Control Hub
The deadline, and the lists the report uses.
The hour the report is due decides whether it holds counts or memories. Set it after a morning walk, not before.
Project
Report due by (time) | 14:00 | Topic 17: the same form, due at 07:00, holds memories.
Prepared by | Site engineers, consolidated by project controls
Part-lost day counts as (days lost) | 0.5
Notice period after an event (days) | 28 | Check your contract: FIDIC 2017 Sub-Clause 20.2.1 uses 28 days.
Trades |  | Plant | Companies | People and roles | Locations | Units | Weather | Why plant is idle | Suppliers | Materials | Report fields
| Piling crew | Piling rig | Piling sub | Site engineer | North piling area | no. | Dry | Standby | Steel supplier | Reinforcement | Labour · headcount
| Rebar gang | Crawler crane | Rebar sub | Site manager | South piling area | m | Overcast | No operator | Aggregates | Blinding stone | Labour · hours
| Concrete gang | Excavator | Concrete sub | Project controls | Raft bay 1 | m² | Showers | Breakdown | Ready-mix concrete | Concrete | Plant · on site / working
| Groundworks | Concrete pump | Groundworks | Project manager | Raft bay 2 | m³ | Rain | Weather | Membrane supplier | Membrane | Work done · quantity
| Supervision | Dumper | Main contractor | Resident engineer | Substation slab | t | Heavy rain | No work front | Pipe supplier | Drainage pipe | Work done · source
| Electricians | Roller |  | HSE officer | East side | kg | Snow | Awaiting materials |  | Formwork | Weather · conditions
| Labourers |  |  | Foreman | West side | h | Fog | Maintenance |  |  | Weather · rainfall
[5 empty] | Site-wide | LS | High wind |  |  |  | Deliveries · quantity
Events · description
Health and safety · entry
Add to these lists here; the drop-downs in the report pick them up. Leave no gaps inside a list.

## 15 Chart data
Chart data | [7 empty] | The Project Control Hub
Behind-the-scenes calculations for the Dashboard: week control and the numbers the four charts plot.
Locked: nothing to type here. Pick the week on the Dashboard (C4); this page follows it.
Chart data
Workable
Part lost
Lost
Week control
First Monday in the log
Weeks in the log
Week start (Monday)
Week end (Sunday)
Reports this week
| Date | Day | People | Revisions | Plant working | Working day | Claims | Key event