## 00 Start
Daily site report |  |  |  | The Project Control Hub
The record nobody reads until a claim, an incident or a test result needs it. Make it one that stands.
The Project Control Hub · free template · example: the example project, 2 to 13 March
EVERY DAY, IN FIVE STEPS · type each fact once, in a log; the report and the Dashboard read from there
1 | 03 Day log → | One line for the day: report no., time issued, weather, rainfall, working day, prepared by. | 1 minute
2 | 04 Resource log → | Every crew and every machine, each against its P6 activity ID: number, hours, idle reason. | 5 minutes
3 | 05 Work done log → | The quantity done on each P6 activity, and where it came from: counted, estimated or not yet reported. | 5 minutes
4 | 06 Event log → | Events, instructions and delays; deliveries in the Delivery log, safety in the Safety log. A claim? Notice calendar. | 3 minutes
5 | 01 Daily report → | Pick the date in B5: the report builds itself. Blanks go to Not yet reported, corrections to the Revision log. | 1 minute
COUNTED, OR REMEMBERED?
| Counted | Somebody measured it today: the survey, the store, the attendance sheet.
| Estimated | A foreman’s figure. Allowed, but labelled, and measured later.
| Not yet reported | The day has not finished producing it. A visible blank beats a quiet wrong number.
TWO WAYS TO JUDGE A DAILY REPORT
| Went out on time | Easy to measure, easy to hit, and easy to game by sending an emptier report earlier.
| Never revised after | Cannot be gamed by hurrying. The Dashboard shows both; the second is the one that matters.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in: only in the log sheets, Setup, Contract hours and P6 activities.
| White, black text | A formula. Leave it alone and it keeps working. The Daily report and Dashboard are all formulas.
| Red | Lost day, not reported, overdue, or an event that could become a claim.
WHAT IS IN THIS FILE
READ AND SEND · built for you
| 01 Daily report | A view, not a form: pick a date and it fills itself from the logs. Ready to send.
| 02 Dashboard | The week, picked in C4: six numbers, productivity, four charts, quantities, key events.
EVERY DAY · type the facts
| 03 Day log | One line a day: the header facts. People, plant, events and claims fill themselves.
| 04 Resource log | Every crew and machine against its P6 activity: man-hours and machine-hours.
| 05 Work done log | One line per P6 activity per day: quantities, with their source.
| 06 Event log | Events, instructions, delays and visitors, with the P6 activity affected.
| 07 Delivery log | Every delivery, with delivery note, short or damaged, and its P6 activity.
| 08 Safety log | Incidents, near misses, toolbox talks and inspections.
FOLLOW UP · close the gaps
| 09 Not yet reported | Explicit blanks, followed up until closed.
| 10 Revision log | Every correction, with the old value, the new one and why.
| 11 Notice calendar | Every event that could become a claim, with its notice deadline.
ONCE PER PROJECT · set up
| 12 P6 activities | The Primavera P6 activity list: paste your P6 export here. Every drop-down reads from it.
| 13 Contract hours | Contract quantity and man-hours per P6 activity: the baseline for productivity.
| 14 Setup | The deadline, the notice period and every drop-down list.
| 15 Chart data | Locked calculations behind the Dashboard charts. Nothing to type here.
EXPLAINED IN
Reporting Topic 17 · The daily report
Contract Topic 1 · The notice behind the entitlement
Example: ten working days of the example project, 2 to 13 March 2026. Tuesday 3 March is logged in full (crews, plant, quantities, events): the day the piling rig hit rock at P17 and P18 and the email to the resident engineer went unanswered except for "noted, discuss Thursday" (Contract Topic 1). Other days keep totals only. P6 IDs, headcounts, quantities, contract hours and weather are illustrative.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## 01 Daily report
Daily site report | [6 empty] | The Project Control Hub
One day, on one page. Every figure says where it came from.
Pick the date in B5. Everything on this page is pulled from the logs: type the facts once, in the Day log, Resource log, Work done log, Delivery log, Event log and Safety log.
Built automatically from the logs for the date in B5. Change the facts in the logs, not here.
Date | 2026-03-03 |  |  | Revision | 1 | raised by each line on the Revision log
Report no. | 41 |  |  | Due by | 14:00
Issued at | 14:00 |  |  | On time? | ✔ on time
Weather, morning | Dry |  |  | Prepared by | Site engineer
Weather, afternoon | Rain |  |  | Checked by
Working conditions | Part lost |  |  | Project | Example project
Rainfall (mm) |  |  |  | Temp. (°C) | 6
LABOUR
Company | Trade | Headcount | Hours each | Man-hours | P6 Activity ID | Note
Piling sub | Piling crew | 6 | 9 | 54 | A1000
Rebar sub | Rebar gang | 8 | 9 | 72 | A1100
Concrete sub | Concrete gang | 6 | 9 | 54 | A1200
Groundworks | Groundworks | 5 | 9 | 45 | A1300
Main contractor | Supervision | 3 | 10 | 30 | INDIRECT
| Total on site | 28 |  | 255
PLANT
Plant |  | On site | Working | Idle | P6 Activity ID | Hours each | Why idle
Piling rig |  | 1 | 1 | 0 | A1000 | 9
Crawler crane |  | 1 | 1 | 0 | A1100 | 9
Excavator |  | 2 | 1 | 1 | A1300 | 9 | No operator
Concrete pump |  | 1 | 0 | 1 | A1200 | 0 | Standby
| Working |  | 3 | 2 |  | 27 | machine-hours
WORK DONE
P6 Activity ID | Activity | Location | Quantity | Unit | Source | Comment
A1000 | Bored piles, north | North piling area | 2 | no. | Counted | P17, P18. Penetration rate changed: see events
A1100 | Raft reinforcement, bay 1 | Raft bay 1 | 3.5 | t | Counted | About 16 hours a tonne
A1200 | Blinding, substation slab | Substation slab | 38 | m² | Counted | Survey completed next morning (revision 1)
A1300 | Drainage run D2 | East side | 24 | m | Estimated | Foreman’s figure; to be measured
DELIVERIES
Supplier | Material | Quantity | Unit | Delivery note | Short or damaged? | P6 Activity ID | Note
Steel supplier | Reinforcement | 12 | t | DN-1182 | N | A1100
Aggregates | Blinding stone | 20 | t | DN-0457 | N | A1200
EVENTS, INSTRUCTIONS, DELAYS, VISITORS
Type | What happened |  |  | P6 Activity ID | Time | Could it become a claim? | Then
Event | Piling rig: penetration rate changed at P17 and P18, consistent with rock. Driller’s log kept. |  |  | A1000 | 10:40 | Y | In the Notice calendar
Instruction | Site engineer emailed the resident engineer; reply "noted, discuss Thursday". No Notice served yet. |  |  | A1000 | 11:15 | Y | In the Notice calendar
Delay | Rain from 15:00: blinding stopped for the day. |  |  | A1200 | 15:00 | N
HEALTH AND SAFETY
Type | What happened |  |  | Location | Time | Reported to | Action taken
THIS REPORT IN NUMBERS
People on site |  | 28
Man-hours |  | 255
Plant working |  | 3
Plant idle |  | 2
Quantities counted |  | 3
Quantities estimated |  | 1
Not yet reported (on the list) |  | 2
Events that could become a claim |  | 2
Deliveries short or damaged |  | 0
Safety incidents and near misses |  | 0

## 02 Dashboard
Daily reports | [8 empty] | The Project Control Hub
Example project · weekly view · log runs 2 Mar to 13 Mar 2026 · due by 14:00
WEEK | 1 |  | Mon 2 Mar to Sun 8 Mar 2026 · week 1 of 2 · 5 reports
REPORTS ON TIME |  | NEVER REVISED |  | WORKING DAYS LOST |  | AVERAGE ON SITE |  | RAISED, NOT REPORTED |  | POSSIBLE CLAIMS
80% |  | 60% |  | 2 |  | 22.6 |  | 2 |  | 2
1 late |  | the measure that matters · 3 revisions |  | 1 lost, 2 part lost |  | people a day · peak 28 |  | raised this week · 2 open in total |  | notices: 2 open, 0 overdue
This week, of 5 reports, 4 went out on time and 3 never changed afterwards. Judge the report by the second number: a report that stands is worth more than one that arrives early and is corrected three times.
THE WEEK IN FOUR CHARTS
WHAT THIS WEEK’S REPORTS RECORD · the evidence a claim will ask for later
Date | Working day | People | Revisions | Claims | Key event
2026-03-02 | Workable | 26 | 0 | 0 | Piling P15 and P16
2026-03-03 | Part lost | 28 | 1 | 2 | Piling rig: penetration rate changed at P17 and P18, consistent with rock. Driller’s log kept.
2026-03-04 | Part lost | 22 | 0 | 0 | Bar schedule revision for bay 2 requested
2026-03-05 | Lost | 10 | 2 | 0 | No pours: heavy rain
2026-03-06 | Workable | 27 | 0 | 0 | Crane booked for 17 March
2026-03-07 |  |  |  |  | no report
2026-03-08 |  |  |  |  | no report
WORK DONE THIS WEEK · quantities by P6 activity, from the Work done log
P6 ID | Activity |  | Unit | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | Week total
A1000 | Bored piles, north |  | no. | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2
A1100 | Raft reinforcement, bay 1 |  | t | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 3.5
A1200 | Blinding, substation slab |  | m² | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 38
A1300 | Drainage run D2 |  | m | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24
PRODUCTIVITY THIS WEEK · earned ÷ actual man-hours against the Contract hours norms · overall 1.01x
P6 ID | Activity |  | Unit | Quantity this week | Norm (mh / unit) | Earned man-hours | Actual man-hours | Productivity this week | Contract man-hours | % complete | Productivity to date
A1000 | Bored piles, north |  | no. | 2 | 25 | 50 | 54 | 0.92593 | 1000 | 5% | 0.92593
A1100 | Raft reinforcement, bay 1 |  | t | 3.5 | 15 | 52.5 | 72 | 0.72917 | 900 | 5.833% | 0.72917
A1200 | Blinding, substation slab |  | m² | 38 | 2 | 76 | 54 | 1.4074 | 300 | 25.33% | 1.4074
A1300 | Drainage run D2 |  | m | 24 | 2 | 48 | 45 | 1.0667 | 240 | 20% | 1.0667
Week | indirect man-hours (not in productivity): 30 |  |  |  |  | 226.5 | 225 | 1.0067
Above 1.00x the gang beat the contract norm; below 1.00x it spent more hours than the job was priced for.
Nobody reads the daily report until a claim, an incident or a test result needs it. Then it cannot be reconstructed.
Formulas:
Key event = IF([WORKING DAYS LOST]="","",[WORKING DAYS LOST]+1)
AVERAGE ON SITE = IF([Key event]="","",[Key event]+1)

## 03 Day log
Day log | [16 empty] | The Project Control Hub
One line per day, so the month can be read at a glance.
Type one line per day here: the header facts only. People, plant, events and not-yet-reported counts fill themselves from the other logs.
Date | Report no. | Issued at | On time? | Revisions | Weather | Working day | People on site | Plant working | Not yet reported | Possible claims | Key event | Weather, morning | Weather, afternoon | Rainfall (mm) | Temp. (°C) | Prepared by | Checked by
2026-03-02 | 40 | 13:40 | Y | 0 | Dry | Workable | 26 | 4 | 0 | 0 | Piling P15 and P16 | Dry | Dry |  |  | Site engineer
2026-03-03 | 41 | 14:00 | Y | 1 | Dry / Rain | Part lost | 28 | 3 | 2 | 2 | Piling rig: penetration rate changed at P17 and P18, consistent with rock. Driller’s log kept. | Dry | Rain |  | 6 | Site engineer
2026-03-04 | 42 | 15:10 | N | 0 | Rain | Part lost | 22 | 3 | 0 | 0 | Bar schedule revision for bay 2 requested | Rain | Rain |  |  | Site engineer
2026-03-05 | 43 | 13:50 | Y | 2 | Heavy rain | Lost | 10 | 1 | 2 | 0 | No pours: heavy rain | Heavy rain | Heavy rain |  |  | Site engineer
2026-03-06 | 44 | 13:30 | Y | 0 | Dry | Workable | 27 | 4 | 0 | 0 | Crane booked for 17 March | Dry | Dry |  |  | Site engineer
2026-03-09 | 45 | 14:20 | N | 0 | Dry | Workable | 29 | 4 | 0 | 0 | Rig back in service | Dry | Dry |  |  | Site engineer
2026-03-10 | 46 | 13:45 | Y | 1 | Dry | Workable | 30 | 4 | 1 | 0 | Ground beams GB1 to GB3 poured | Dry | Dry |  |  | Site engineer
2026-03-11 | 47 | 13:55 | Y | 0 | Showers | Part lost | 25 | 3 | 0 | 0 | Membrane delivery not confirmed | Showers | Showers |  |  | Site engineer
2026-03-12 | 48 | 13:40 | Y | 0 | Dry | Workable | 28 | 4 | 0 | 0 | Raft rebar bay 1 continues | Dry | Dry |  |  | Site engineer
2026-03-13 | 49 | 13:35 | Y | 0 | Dry | Workable | 27 | 4 | 0 | 0 | Weekly meeting | Dry | Dry |  |  | Site engineer

## 04 Resource log
Resource log | [10 empty] | The Project Control Hub
One line per resource per P6 activity per day: man-hours and machine-hours, ready to load into P6 as actual units.
Type the facts here, once. One line per crew or machine per P6 activity per day. For plant: Number = working, On site = total on site.
Date | P6 Activity ID | Activity (from P6) | WBS (from P6) | Type | Resource | Company | Number | Hours each | Total hours | On site (plant) | Why idle
2026-03-03 | A1000 | Bored piles, north | SITE.FND.PIL | Labour | Piling crew | Piling sub | 6 | 9 | 54
2026-03-03 | A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF | Labour | Rebar gang | Rebar sub | 8 | 9 | 72
2026-03-03 | A1200 | Blinding, substation slab | SITE.SUB.SLB | Labour | Concrete gang | Concrete sub | 6 | 9 | 54
2026-03-03 | A1300 | Drainage run D2 | SITE.EXT.DRN | Labour | Groundworks | Groundworks | 5 | 9 | 45
2026-03-03 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | Supervision | Main contractor | 3 | 10 | 30
2026-03-03 | A1000 | Bored piles, north | SITE.FND.PIL | Plant | Piling rig |  | 1 | 9 | 9 | 1
2026-03-03 | A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF | Plant | Crawler crane |  | 1 | 9 | 9 | 1
2026-03-03 | A1300 | Drainage run D2 | SITE.EXT.DRN | Plant | Excavator |  | 1 | 9 | 9 | 2 | No operator
2026-03-03 | A1200 | Blinding, substation slab | SITE.SUB.SLB | Plant | Concrete pump |  | 0 | 0 | 0 | 1 | Standby
2026-03-02 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 26
2026-03-02 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4
2026-03-04 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 22
2026-03-04 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 3 |  |  | 3
2026-03-05 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 10
2026-03-05 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 1 |  |  | 1
2026-03-06 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 27
2026-03-06 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4
2026-03-09 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 29
2026-03-09 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4
2026-03-10 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 30
2026-03-10 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4
2026-03-11 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 25
2026-03-11 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 3 |  |  | 3
2026-03-12 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 28
2026-03-12 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4
2026-03-13 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Labour | All trades (no breakdown kept) |  | 27
2026-03-13 | INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND | Plant | All plant (no breakdown kept) |  | 4 |  |  | 4

## 05 Work done log
Work done log | [7 empty] | The Project Control Hub
One line per P6 activity per day: the quantities the Dashboard adds up by week.
Type the facts here, once: one line per P6 activity per day. The Daily report and the Dashboard read from here.
Date | P6 Activity ID | Activity (from P6) | WBS (from P6) | Location | Quantity | Unit | Source | Comment
2026-03-03 | A1000 | Bored piles, north | SITE.FND.PIL | North piling area | 2 | no. | Counted | P17, P18. Penetration rate changed: see events
2026-03-03 | A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF | Raft bay 1 | 3.5 | t | Counted | About 16 hours a tonne
2026-03-03 | A1200 | Blinding, substation slab | SITE.SUB.SLB | Substation slab | 38 | m² | Counted | Survey completed next morning (revision 1)
2026-03-03 | A1300 | Drainage run D2 | SITE.EXT.DRN | East side | 24 | m | Estimated | Foreman’s figure; to be measured

## 06 Event log
Event log | [8 empty] | The Project Control Hub
Events, instructions, delays, visitors: one line each. The Daily report and the Notice calendar read from here.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Type | What happened | P6 Activity ID | Activity (from P6) | WBS (from P6) | Time | Could it become a claim? | Then
2026-03-02 | Event | Piling P15 and P16 |  |  |  |  | N
2026-03-03 | Event | Piling rig: penetration rate changed at P17 and P18, consistent with rock. Driller’s log kept. | A1000 | Bored piles, north | SITE.FND.PIL | 10:40 | Y | In the Notice calendar
2026-03-03 | Instruction | Site engineer emailed the resident engineer; reply "noted, discuss Thursday". No Notice served yet. | A1000 | Bored piles, north | SITE.FND.PIL | 11:15 | Y | In the Notice calendar
2026-03-03 | Delay | Rain from 15:00: blinding stopped for the day. | A1200 | Blinding, substation slab | SITE.SUB.SLB | 15:00 | N
2026-03-04 | Event | Bar schedule revision for bay 2 requested |  |  |  |  | N
2026-03-05 | Event | No pours: heavy rain |  |  |  |  | N
2026-03-06 | Event | Crane booked for 17 March |  |  |  |  | N
2026-03-09 | Event | Rig back in service |  |  |  |  | N
2026-03-10 | Event | Ground beams GB1 to GB3 poured |  |  |  |  | N
2026-03-11 | Event | Membrane delivery not confirmed |  |  |  |  | N
2026-03-12 | Event | Raft rebar bay 1 continues |  |  |  |  | N
2026-03-13 | Event | Weekly meeting |  |  |  |  | N

## 07 Delivery log
Delivery log | [9 empty] | The Project Control Hub
Every delivery that arrives on site, one line each.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Supplier | Material | Quantity | Unit | Delivery note | Short or damaged? | P6 Activity ID | Activity (from P6) | WBS (from P6) | Note
2026-03-03 | Steel supplier | Reinforcement | 12 | t | DN-1182 | N | A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF
2026-03-03 | Aggregates | Blinding stone | 20 | t | DN-0457 | N | A1200 | Blinding, substation slab | SITE.SUB.SLB

## 08 Safety log
Safety log | [5 empty] | The Project Control Hub
Incidents, near misses, toolbox talks and inspections, one line each.
Type the facts here, once. Blue cells are inputs; the Daily report builds itself from this log when you pick a date.
Date | Type | What happened | Location | Time | Reported to | Action taken

## 09 Not yet reported
Not yet reported | [6 empty] | The Project Control Hub
Fields the day could not close, published as blanks and followed up.
"We will correct it tomorrow" is a promise projects break. A list somebody closes is not.
Report date | Field | Who will supply it | Expected by | Closed on | Closed in revision | Days open | Status
2026-03-03 | Blinding quantity, substation slab | Site engineer | 2026-03-04 | 2026-03-04 | 1 | 1 | Closed
2026-03-03 | Drainage run D2 length (estimated, to be measured) | Foreman | 2026-03-04 |  |  | 10 | Overdue
2026-03-05 | Rainfall total | Site engineer | 2026-03-06 | 2026-03-06 | 2 | 1 | Closed
2026-03-05 | Drainage run D3 length | Foreman | 2026-03-06 |  |  | 8 | Overdue
2026-03-10 | GB3 concrete volume | Site engineer | 2026-03-11 | 2026-03-11 | 1 | 1 | Closed

## 10 Revision log
Revision log | [7 empty] | The Project Control Hub
What changed, when, and why. Without it, one day becomes three versions of itself.
One line per correction. The Daily report counts the lines for its date and shows the revision number.
Report date | Report no. | New revision | Field | Old value | New value | Reason | Changed by | Changed on
2026-03-03 | 41 | 1 | Work done · quantity | Not yet reported | 38 m² | A1200 blinding: survey completed next morning | Site engineer | 2026-03-04
2026-03-05 | 43 | 1 | Labour · headcount | 6 | 4 | Groundworks: two left at 10:00 when the rain set in | Site manager | 2026-03-06
2026-03-05 | 43 | 2 | Weather · rainfall | Not yet reported | 31 mm | Gauge read next morning | Site engineer | 2026-03-06
2026-03-10 | 46 | 1 | Work done · quantity | Not yet reported | 14.5 m³ | GB3 concrete volume: delivery tickets reconciled | Site engineer | 2026-03-11

## 11 Notice calendar
Notice calendar | [9 empty] | The Project Control Hub
Every event that could become a claim, with the date its notice is due.
The contract clock starts on the day of the event, not on the day somebody remembers it.
Event date | Report no. | Event | Notice due by | Notice sent on | Days left | Status | Who sends it | P6 Activity ID | Activity (from P6) | WBS (from P6)
2026-03-03 | 41 | Piling rig: rock at P17 and P18 (penetration rate changed) | 2026-03-31 |  | 18 | Open | Project manager | A1000 | Bored piles, north | SITE.FND.PIL
2026-03-03 | 41 | Resident engineer: "noted, discuss Thursday"; no Notice served | 2026-03-31 |  | 18 | Open | Project manager | A1000 | Bored piles, north | SITE.FND.PIL
Formulas:
Notice due by = IF([Event date]="","",[Event date]+'14 Setup'!$B10)

## 12 P6 activities
P6 activities | [14 empty] | The Project Control Hub
The activity IDs the report books work against, from the Primavera P6 programme.
Paste a fresh P6 export (Activity ID, Activity Name, WBS, budgeted quantity, budgeted man-hours) here when the programme is re-baselined. Grey columns calculate themselves from every daily report.
Activity ID | Activity name | WBS | Location | Unit | Budgeted quantity (P6) | Budgeted man-hours (P6) | Quantity to date | Quantity % complete | Remaining quantity | Actual man-hours to date | Man-hours % spent | Earned man-hours | Productivity (earned ÷ actual) | Last reported | Notes
A1000 | Bored piles, north | SITE.FND.PIL | North piling area | no. | 40 | 1000 | 2 | 5% | 38 | 54 | 5.4% | 50 | 0.92593 | 2026-03-03
A1010 | Bored piles, south | SITE.FND.PIL | South piling area | no. | 40 | 1000 | 0 | 0% | 40 | 0 | 0% | 0 |  | not yet
A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF | Raft bay 1 | t | 60 | 900 | 3.5 | 5.833% | 56.5 | 72 | 8% | 52.5 | 0.72917 | 2026-03-03
A1110 | Raft reinforcement, bay 2 | SITE.FND.RAF | Raft bay 2 | t | 60 | 900 | 0 | 0% | 60 | 0 | 0% | 0 |  | not yet
A1200 | Blinding, substation slab | SITE.SUB.SLB | Substation slab | m² | 150 | 300 | 38 | 25.33% | 112 | 54 | 18% | 76 | 1.4074 | 2026-03-03
A1300 | Drainage run D2 | SITE.EXT.DRN | East side | m | 120 | 240 | 24 | 20% | 96 | 45 | 18.75% | 48 | 1.0667 | 2026-03-03
A1310 | Drainage run D3 | SITE.EXT.DRN | East side | m | 100 | 200 | 0 | 0% | 100 | 0 | 0% | 0 |  | not yet
A1400 | Ground beams GB1 to GB3 | SITE.FND.GB | Raft bay 1 | m³ | 45 | 360 | 0 | 0% | 45 | 0 | 0% | 0 |  | not yet
INDIRECT | Indirect work: supervision, welfare, cleaning | SITE.IND |  | h |  |  | 0 |  |  | 30 |  |  |  | not yet | Not loaded to P6 activities; kept for the hours total
Formulas:
Last reported = IF([Activity ID]="","",IFERROR(1/(1/MAXIFS('05 Work done log'!$A7:A506,'05 Work done log'!$B7:B506,[Activity ID])),"not yet"))

## 13 Contract hours
Contract hours | [10 empty] | The Project Control Hub
Contract (budgeted) quantity and man-hours for each P6 activity, and how the job is doing against them.
Blue cells are inputs: take them from the priced bill or the P6 baseline. Everything else fills itself from the Work done log and the Resource log.
Productivity = earned man-hours ÷ actual man-hours. Above 1.00 the gang is beating the contract norm; below 1.00 it is spending more hours than the job was priced for.
P6 Activity ID | Activity | WBS (from P6) | Unit | Contract quantity | Contract man-hours | Norm (man-hours per unit) | Quantity to date | Actual man-hours to date | Earned man-hours to date | % complete | Productivity to date
A1000 | Bored piles, north | SITE.FND.PIL | no. | 40 | 1000 | 25 | 2 | 54 | 50 | 5% | 0.92593
A1010 | Bored piles, south | SITE.FND.PIL | no. | 40 | 1000 | 25 | 0 | 0 | 0 | 0%
A1100 | Raft reinforcement, bay 1 | SITE.FND.RAF | t | 60 | 900 | 15 | 3.5 | 72 | 52.5 | 5.833% | 0.72917
A1110 | Raft reinforcement, bay 2 | SITE.FND.RAF | t | 60 | 900 | 15 | 0 | 0 | 0 | 0%
A1200 | Blinding, substation slab | SITE.SUB.SLB | m² | 150 | 300 | 2 | 38 | 54 | 76 | 25.33% | 1.4074
A1300 | Drainage run D2 | SITE.EXT.DRN | m | 120 | 240 | 2 | 24 | 45 | 48 | 20% | 1.0667
A1310 | Drainage run D3 | SITE.EXT.DRN | m | 100 | 200 | 2 | 0 | 0 | 0 | 0%
A1400 | Ground beams GB1 to GB3 | SITE.FND.GB | m³ | 45 | 360 | 8 | 0 | 0 | 0 | 0%
Note on E6: Example figures only (8 activities). Replace with the contract bill of quantities / P6 budgeted units before using the productivity numbers.

## 14 Setup
Setup | [10 empty] | The Project Control Hub
The deadline, and the lists the report uses.
The hour the report is due decides whether it holds counts or memories. Set it after a morning walk, not before.
Project | Example project
Report due by (time) | 14:00 | Topic 17: the same form, due at 07:00, holds memories.
Prepared by | Site engineers, consolidated by project controls
Part-lost day counts as (days lost) | 0.5
Notice period after an event (days) | 28 | Check your contract: FIDIC 2017 Sub-Clause 20.2.1 uses 28 days.
Trades |  | Plant | Companies | People and roles | Locations | Units | Weather | Why plant is idle | Suppliers | Materials | Report fields
| Piling crew | Piling rig | Piling sub | Site engineer | North piling area | no. | Dry | Standby | Steel supplier | Reinforcement | Labour · headcount
| Rebar gang | Crawler crane | Rebar sub | Site manager | South piling area | m | Overcast | No operator | Aggregates | Blinding stone | Labour · hours
| Concrete gang | Excavator | Concrete sub | Project controls | Raft bay 1 | m² | Showers | Breakdown | Ready-mix concrete | Concrete | Plant · on site / working
| Groundworks | Concrete pump | Groundworks | Project manager | Raft bay 2 | m³ | Rain | Weather | Membrane supplier | Membrane | Work done · quantity
| Supervision | Dumper | Main contractor | Resident engineer | Substation slab | t | Heavy rain | No work front | Pipe supplier | Drainage pipe | Work done · source
| Electricians | Roller |  | HSE officer | East side | kg | Snow | Awaiting materials |  | Formwork | Weather · conditions
| Labourers |  |  | Foreman | West side | h | Fog | Maintenance |  |  | Weather · rainfall
[5 empty] | Site-wide | LS | High wind |  |  |  | Deliveries · quantity
Events · description
Health and safety · entry
Add to these lists here; the drop-downs in the report pick them up. Leave no gaps inside a list.

## 15 Chart data
Chart data | [7 empty] | The Project Control Hub
Behind-the-scenes calculations for the Dashboard: week control and the numbers the four charts plot.
Locked: nothing to type here. Pick the week on the Dashboard (C4); this page follows it.
Chart data
| Workable | 2
| Part lost | 2
| Lost | 1
Week control
| First Monday in the log | 2026-03-02
| Weeks in the log | 2
| Week start (Monday) | 2026-03-02
| Week end (Sunday) | 2026-03-08
| Reports this week | 5
| Date | Day | People | Revisions | Plant working | Working day | Claims | Key event
| 2026-03-02 | Mon 2 | 26 | 0 | 4 | Workable | 0 | Piling P15 and P16
| 2026-03-03 | Tue 3 | 28 | 1 | 3 | Part lost | 2 | Piling rig: penetration rate changed at P17 and P18, consistent with rock. Driller’s log kept.
| 2026-03-04 | Wed 4 | 22 | 0 | 3 | Part lost | 0 | Bar schedule revision for bay 2 requested
| 2026-03-05 | Thu 5 | 10 | 2 | 1 | Lost | 0 | No pours: heavy rain
| 2026-03-06 | Fri 6 | 27 | 0 | 4 | Workable | 0 | Crane booked for 17 March
| 2026-03-07 | Sat 7 |  | #N/A | #N/A
| 2026-03-08 | Sun 8 |  | #N/A | #N/A
Formulas:
Date = IF([Date, row above]="","",[Date, row above]+1)