## Start
Earned value calculator |  |  | The Project Control Hub
Three numbers a month in; where the job ends, what recovery would take, and how late it is, out.
The Project Control Hub · free template
EVERY MONTH, IN FIVE STEPS
1 | Setup → | Once: BAC, duration, the date month 1 ends. Every month: change "This report: month". | 1 minute
2 | Monthly → | Once: the baseline PV, month by month. Every month: EV and AC for the new row. | 5 minutes
3 | Work packages → | EV and AC by package, each measured by a rule agreed in advance. The totals check against Monthly. | 20 minutes
4 | Results → | Read it. Every measure, with one line on what it means, and four ways to forecast the finish. | 5 minutes
5 | Dashboard → | Take it to the meeting. Say the plain-English paragraph out loud. | —
THE THREE NUMBERS
| PV · the promise | What the baseline said would be built by now. Comes from the schedule, once.
| EV · what is standing | The budget of the work actually done, measured. Never "about eighty percent".
| AC · what was paid | What has left the bank. Ask accounts.
EV against AC tells you about cost. EV against PV tells you about time. PV against AC tells you nothing.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Teal row | The reporting month.
| Amber | An index between 0.90 and 1.00: watch it.
| Red | An index under 0.90, a negative variance, or a TCPI the site has never achieved.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, a paragraph in plain English, four charts and the work packages.
| Setup | BAC, duration, the reporting month.
| Monthly | PV, EV and AC month by month, with CPI, SPI, earned schedule and the forecast curve.
| Results | Every measure for the month, explained, and four EAC methods side by side.
| Work packages | EV and AC by package, so you can see where the money goes.
EXPLAINED IN
Schedule Topic 18 · EVM fundamentals
Schedule Topic 19 · EVM analysis
Schedule Topic 20 · Forecasting
Cost & Cash Topic 6 · Why CPI flatters a tender sum
Blank: twenty-four months and twenty work packages ready to fill. The example file shows month six of the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Earned value | [7 empty] | The Project Control Hub
CPI · COST | SPI(t) · TIME |  | ESTIMATE AT COMPLETION |  | OVERRUN AT COMPLETION |  | TCPI · NEEDED FROM NOW |  | STILL TO PAY OUT | Chart data
CPI achieved
Best month
TCPI needed
THE THREE NUMBERS, AND WHERE THEY LEAD
WHERE THE MONEY IS LOST, AND WHAT RECOVERY WOULD TAKE
WORK PACKAGES
Package |  | Budget | PV | EV | AC | CV | CPI | SPI | Flag
Everything on this page reads from Monthly, Results and Work packages.

## Setup
Setup | The Project Control Hub
The budget, the duration and the month you are reporting.
Change "This report: month" every month. Everything else reads from here.
Project
Budget at completion, BAC ($) | The budget you control. A tender sum carries overhead, profit and reserve: dividing invoices by it flatters CPI (Cost & Cash Topics 5 and 6).
Planned duration (months)
This report: month | The row of the Monthly sheet the Dashboard and Results read.
Month 1 ends on | Optional. Dates the Monthly rows and the forecast finish.
Prepared by

## Monthly
Monthly | [12 empty] | The Project Control Hub
The three numbers every month: the promise (PV), what is standing (EV), what has been paid (AC).
PV comes from the baseline once. Each month add EV (measured, never "about eighty percent") and AC (ask accounts).
Month | Month end | Planned value, PV (cumulative $) | Earned value, EV (cumulative $) | Actual cost, AC (cumulative $) | Cost variance, CV ($) | Schedule variance, SV ($) | CPI | SPI ($) | Earned schedule (months) | SPI(t) | Delay (months) | CPI this month | Forecast cost if nothing changes ($) | Target 1.0 | CPI | SPI(t) | Forecast cost if nothing changes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Earned schedule: the month the baseline said you would reach today’s EV. CPI this month: the efficiency of this month alone, so the best month can be found.
Formulas:
Month end = IF(Setup!$B10="","",EOMONTH(Setup!$B10,[Month]-1))
Note on O6: Columns O to R only feed the charts. #N/A there is deliberate: it makes a gap instead of a drop to zero.

## Results
Results |  | The Project Control Hub
Every measure for the reporting month, with what it means in one line.
Nothing to fill in here. It reads the Monthly row for "This report: month".
THIS MONTH
Planned value, PV ($) |  | The promise: what the baseline said would be built by now.
Earned value, EV ($) |  | What is standing: the budget of the work actually done.
Actual cost, AC ($) |  | What has left the bank. Invoices, not opinions.
Cost performance index, CPI = EV ÷ AC |  | Cents of work bought with every dollar spent.
Schedule performance index, SPI = EV ÷ PV |  | In money. Creeps back to 1.0 at the end, even on a late job.
Cost variance, CV = EV − AC ($) |  | Negative: the work cost more than it was worth.
Schedule variance, SV = EV − PV ($) |  | Negative: less built than promised, measured in money.
AT COMPLETION
Budget at completion, BAC ($) |  | From Setup.
Estimate at completion, EAC = BAC ÷ CPI ($) |  | Where this ends if nothing changes.
Variance at completion, VAC = BAC − EAC ($) |  | Negative: the overrun somebody has to find.
Estimate to complete, ETC = EAC − AC ($) |  | Still to be paid out. A cash-flow number.
To-complete index, TCPI = (BAC − EV) ÷ (BAC − AC) |  | The efficiency needed from tomorrow to still hit the budget.
Improvement needed over the CPI achieved |  | How much better than the proven rate the rest of the job must be.
Best single month so far (CPI this month) |  | The best the site has actually done.
Verdict
IN MONTHS, NOT MONEY
Earned schedule, ES (months) |  | The month the plan said you would reach today’s EV.
Actual time, AT (months) |  | The reporting month.
Schedule performance in time, SPI(t) = ES ÷ AT |  | Unlike SPI, it does not drift back to 1.0.
Delay to date (months) = AT − ES |  | One number a site manager understands.
Forecast duration at this pace (months) |  | Planned duration ÷ SPI(t). A trend, not a promise.
Forecast finish |  | The month that pace lands in.
FOUR WAYS TO FORECAST THE FINISH COST
Method | EAC ($) | When it fits
1 · BAC ÷ CPI |  | Performance so far continues. The default, and the one in the lessons.
2 · AC + (BAC − EV) |  | The overrun was a one-off and the rest goes to budget. Prove it before you use it.
3 · AC + (BAC − EV) ÷ (CPI × SPI) |  | Cost and schedule both drag: lateness costs money. Usually the most pessimistic.
4 · AC + a bottom-up estimate of what is left |  | Re-estimate the remaining work from scratch. Type it below.
Bottom-up estimate of the remaining work ($) |  | Optional. Leave empty if you have not re-estimated.
IN PLAIN ENGLISH
If the tender sum is your BAC, the CPI is flattered: overhead, profit and reserve sit inside it. Build the forecast on the budget you control.

## Work packages
Work packages | [12 empty] | The Project Control Hub
Where the money is being lost: EV and AC for each package, measured by a rule decided in advance.
Pick the measuring rule before the work starts, never after. Units complete wherever there is something to count.
Work package | Budget ($) | How EV is measured | Planned % to date | Measured % complete | PV ($) | EV ($) | AC ($) | CV ($) | SV ($) | CPI | SPI | Flag | The rule, in words
Total
Check against the Monthly sheet
MEASURING RULES
Units complete | Count something: piles, metres, tonnes. The most honest rule wherever there is something to count.
Milestones | Fixed weights for fixed steps, agreed in advance. Good for equipment and long single items.
0/100 | Nothing until it is finished. For short tasks, under one reporting period.
50/50 | Half when it starts, half when it finishes. For tasks spanning two periods.
Level of effort | Earns with the calendar. Use only for support work; it hides progress problems.