## Start
Notice and time-bar calendar
Every clock in the contract, and the days left on each, counted from when you became aware.
The Project Control Hub · free template
FIVE STEPS
1 | Setup → | Leave "As at" on today. Pick the contract form: it decides who the Notice goes to. | 1 minute
2 | Events → | Anything that might become a claim gets a row the day somebody notices it: a driller’s log, a short delivery, a level that does not match. Write what fixed the date. | 2 minutes each
3 | Events → | When the Notice goes: its date and the four tests. When the detailed claim goes: its date, and whether the contractual basis is in it. | —
4 | Engineer clocks → | The Engineer’s 14 and 7 days. If they pass in silence, the position moves your way. | 1 minute each
5 | Determinations → | Every determination, the day it lands. 28 days, and no way back. | 1 minute each
FOUR TESTS OF A NOTICE · sub-clause 1.3
| In writing | A paper original signed by the authorised representative, or from the named electronic system.
| Identified as a Notice | It says it is a Notice. An accurate email that does not is not one.
| Delivered the stated way | By hand or courier against receipt, or through the stated system.
| To the stated address | The address in the Contract Data, not the person you speak to every morning.
THREE BANDS
| Ends a right | Notice of Claim 28 d, detailed claim 84 d, Notice of Dissatisfaction 28 d.
| Runs for you | The Engineer’s 14 days on a late Notice, 14 on a lapse, 7 on a challenge.
| Procedure | Consultation, programme, suspension: stages, not bars. Panic here is expensive.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, a paragraph, the next twelve deadlines, and two charts.
| Setup | As at, contract form, warning window.
| The clocks | All eleven periods with clause, consequence, band and rescue.
| Events | The log: dates, the four tests, both claim clocks, status and the next action.
| Engineer clocks | The silences that run for you.
| Determinations | The clock with no rescue.
| Deadlines | A helper list the Dashboard sorts. Nothing to fill in.
EXPLAINED IN
Contract Topic 1 · The notice behind the entitlement
Contract Topic 10 · Notices and time bars
Blank: thirty events, twenty Engineer clocks and twenty determinations ready to fill. "As at" is today.
Clause numbers follow FIDIC 2017 as used in the lessons. Check your own contract. Free to use and adapt. https://theprojectcontrolhub.com/

## Dashboard
Notices and time bars | [5 empty] | The Project Control Hub
OPEN EVENTS |  | NOTICES DUE SOON | 28 DAYS PASSED, NO NOTICE | LATE NOTICES AT RISK | DETAILED CLAIMS DUE ≤ 14 DAYS |  | NO-RESCUE CLOCKS OPEN
THE NEXT DEADLINES, EARLIEST FIRST · missed ones at the top
Deadline | Days left | Event / item |  | Clock |  | Rescue
HOW MUCH TIME IS LEFT
Red ends a right · green runs for you · grey is procedure
Everything on this page reads from Setup, Events, Engineer clocks and Determinations.

## Setup
Setup |  | The Project Control Hub
The date the calendar counts from, and the contract form.
"As at" is today unless you type a date. Every days-left figure counts from it.
Project
As at |  | Today by default. The example is fixed at 41 days after the rock.
Contract form | Red | Red, Yellow or Silver Book (FIDIC 2017), as used in the lessons.
Notices go to |  | Red and Yellow: the Engineer. Silver: there is no Engineer, so the other Party.
Warn me this many days ahead | 7 | Deadlines inside this window turn amber.
Prepared by
Clause numbers follow the FIDIC 2017 Red and Yellow Books as used in the Contract track. Check the periods in your own contract before relying on them.

## The clocks
The clocks, on one page |  |  |  |  | The Project Control Hub
Three end a right, three run for you, five are procedure.
Both claim clocks start the day you became aware, or should have become aware, of the event.
Days | Clause | What it is | If missed | Band | Rescue
28 | 20.2.1 | Notice of Claim | Entitlement gone: the other Party is discharged | Ends a right | Engineer silent for 14 days
84 | 20.2.4 | Fully detailed Claim, with the contractual basis | The Notice of Claim lapses | Ends a right | Engineer silent for 14 days
28 | 3.7.5 | Notice of Dissatisfaction with a determination | Final and binding | Ends a right | None
14 | 20.2.2 | Engineer says your Notice was late | If silent, your Notice is valid | Runs for you | —
7 | 3.5 | Engineer answers your challenge to an instruction | If silent, the instruction is revoked | Runs for you | —
14 | 20.2.4 | Engineer declares a lapse | If silent, your Notice survives | Runs for you | —
42 | 3.7.3 | Consultation to reach agreement | Moves to determination | Procedure | —
28 | 8.3 | Initial programme | A breach, not a bar | Procedure | —
28 | 2.4 | Employer shows it can pay | Opens 16.1 | Procedure | —
21 | 16.1 | Wait before suspending | A floor, not a deadline | Procedure | —
42 | 3.6 | Notice of a new Engineer | 14 days to object | Procedure | —
Serving the Notice on day 27 leaves 57 days for the detailed claim, not 84: both clocks started together.
The Notice of Dissatisfaction is the only fatal clock with no way back. It arrives when everybody is tired and the argument feels finished.

## Events
Events | [21 empty] | The Project Control Hub
One row per event that might become a claim. The clock starts when you became aware, not when you decided to claim.
Fill the yellow cells. The deadlines, the days left, the status and the next action work themselves out.
ID | Event | Became aware (date) | What fixed that date | Money at stake ($) | Owner | Notice served (date) | In writing | Identified as a Notice | Delivered the stated way | To the stated address | Notice valid? | 28-day deadline | Days left (Notice) | Engineer objected to a late Notice on | 84-day deadline | Days left (claim) | Detailed claim submitted (date) | Contractual basis stated? | Notice status | Claim status | Next action | Note
E01
E02
E03
E04
E05
E06
E07
E08
E09
E10
E11
E12
E13
E14
E15
E16
E17
E18
E19
E20
E21
E22
E23
E24
E25
E26
E27
E28
E29
E30

## Engineer clocks
Engineer clocks | [7 empty] | The Project Control Hub
Somebody else’s deadline. If nothing comes back, the position moves your way.
Diarise these precisely: nobody is going to tell you they have expired.
Ref | About | Clock | Starts (date) | Days | Ends | Days left | Engineer responded on | Status
S01
S02
S03
S04
S05
S06
S07
S08
S09
S10
S11
S12
S13
S14
S15
S16
S17
S18
S19
S20

## Determinations
Determinations | [6 empty] | The Project Control Hub
The clock with no rescue: 28 days to give a Notice of Dissatisfaction.
Log every determination the day it lands. Nobody else will tell you this clock has started.
Ref | Determination about | Event ID | Received (date) | Notice of Dissatisfaction deadline | Days left | Notice of Dissatisfaction given (date) | Status
D01
D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
D14
D15
D16
D17
D18
D19
D20

## Deadlines
Deadlines
Every open deadline in one list. The Dashboard reads it; nothing to fill in here.
Deadline | Event / item | Clock | Rescue | Sort key
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Claim · 28 d | Engineer silent 14 days
|  | Detailed claim · 84 d | Engineer silent 14 days
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
|  | Notice of Dissatisfaction · 28 d | None
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you
Runs for you