## Start
Risk register
Written as sentences, priced in money, split into what information can fix and what only money can cover.
The Project Control Hub · free template
A REVIEW, IN SIX STEPS
1 | Setup → | Set the review date and the contingency you carry. | 1 minute
2 | Register → | Write each risk as one sentence: Because [a fact today], [an uncertain event] may occur, which would lead to [an effect in money or days]. The Sentence column checks all three parts. | per risk
3 | Register → | Kind: ask the one question. If finding out would shrink it, it is epistemic; if not, aleatory. | per risk
4 | Register → | Money: probability and impact give the expected value. For every epistemic risk, write what it would cost to find out. A zero is usually an email nobody has sent. | per risk
5 | Register → | Response: a type, the action, its price, one person, a date, and the condition that closes the risk. | per risk
6 | Dashboard → | Read it at the review. Then copy the "This review" row into History. | 5 minutes
THE ONE QUESTION
| Epistemic | The answer already exists somewhere. Spend money finding out and it gets smaller. It wants information: a borehole, a phone call, a credit check.
| Aleatory | It has not happened yet, so nobody can know it. It wants money: measure the spread and hold contingency against it.
| Mixed | Part countable today, part not. Say so rather than forcing it into one column.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Green | Done, complete, or free to resolve.
| Amber | Something is missing: a part of the sentence, a price, a date.
| Red | Overdue, or an open risk with nobody against it.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, four charts and the ten largest open risks.
| Setup | Review date, contingency, and the team and category lists.
| Register | Forty rows: sentence, kind, money, response, owner, date, status.
| History | One row per review, for the exposure trend.
EXPLAINED IN
Risk Topic 4 · Writing a risk as a sentence
Risk Topic 6 · Why the matrix misleads
Risk Topic 8 · Aleatory and epistemic uncertainty
Risk Topic 13 · Response strategies
Blank: forty rows ready to fill. The example file shows the fourteen risks of the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Risk register | [6 empty] | The Project Control Hub
TOTAL EXPECTED VALUE | EPISTEMIC · BUY INFORMATION |  | FREE TO RESOLVE |  | RESPONSE SPEND | CONTINGENCY CARRIED |  | RESPONSES OVERDUE | Chart data (formulas)
Top 10 by expected value
The one question for every line: if I spent money finding out, would the uncertainty get smaller? Yes → epistemic: buy information. No → aleatory: hold money.
WHERE THE MONEY IS
Expected value by kind
Epistemic
Aleatory
Mixed
Epistemic: expected value against cost to find out
[9 empty] | Risk | Expected value | Cost to find out
BUY INFORMATION OR HOLD MONEY
THE TEN LARGEST OPEN RISKS
Risk |  | Kind | EV ($) | Response | Owner | Due | Response status | Overdue
Everything on this page reads from the Register. A red Owner cell is an open risk with nobody against it.

## Setup
Setup | The Project Control Hub
The review date, the contingency you carry, and the lists the register uses.
Change the review date at every review. Overdue responses are counted against it.
Project
Review number
Review date (as at)
Contingency carried ($) | Risk Topic 1: the 5% rule gave $47,553.
Prepared by
Team (Owner drop-down) | Categories (Category drop-down)

## Register
Risk register | [21 empty] | The Project Control Hub
One risk per row, written as a sentence, priced in money, with one person against the response.
The test for Kind: if you spent money finding out, would the uncertainty get smaller? Yes = Epistemic. No = Aleatory.
ID | Risk | Because… (a fact today) | …may occur (the uncertain event) | …which would lead to (the effect) | Sentence | Category | Kind | Probability | Impact ($) | Expected value ($) | Cost to find out ($) | Value of finding out | Response | Response action | Response cost ($) | Owner | Due | Response status | Closes when | Risk status | Days overdue | Note | r | e
R01
R02
R03
R04
R05
R06
R07
R08
R09
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
Summary
Open risks
Total expected value ($)
epistemic ($)
aleatory ($)
mixed ($)
Epistemic risks
Cost to resolve the epistemic risks ($)
Epistemic risks that cost nothing to resolve
Total response spend ($)
Responses priced
Responses done
Open risks with no owner
Responses overdue
Sentences incomplete

## History
History | [6 empty] | The Project Control Hub
One row per review, so the trend is visible: is the register getting shorter and cheaper?
At each review: copy the blue "This review" row and Paste Special → Values into the next empty row.
This review (live)
Review | Date | Open risks | Total EV ($) | Epistemic EV ($) | Aleatory EV ($) | Contingency ($) | Response spend ($)