## Start
Risk register
Written as sentences, priced in money, split into what information can fix and what only money can cover.
The Project Control Hub · free template · example: the fourteen risks of the example project
A REVIEW, IN SIX STEPS
1 | Setup → | Set the review date and the contingency you carry. | 1 minute
2 | Register → | Write each risk as one sentence: Because [a fact today], [an uncertain event] may occur, which would lead to [an effect in money or days]. The Sentence column checks all three parts. | per risk
3 | Register → | Kind: ask the one question. If finding out would shrink it, it is epistemic; if not, aleatory. | per risk
4 | Register → | Money: probability and impact give the expected value. For every epistemic risk, write what it would cost to find out. A zero is usually an email nobody has sent. | per risk
5 | Register → | Response: a type, the action, its price, one person, a date, and the condition that closes the risk. | per risk
6 | Dashboard → | Read it at the review. Then copy the "This review" row into History. | 5 minutes
THE ONE QUESTION
| Epistemic | The answer already exists somewhere. Spend money finding out and it gets smaller. It wants information: a borehole, a phone call, a credit check.
| Aleatory | It has not happened yet, so nobody can know it. It wants money: measure the spread and hold contingency against it.
| Mixed | Part countable today, part not. Say so rather than forcing it into one column.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Green | Done, complete, or free to resolve.
| Amber | Something is missing: a part of the sentence, a price, a date.
| Red | Overdue, or an open risk with nobody against it.
WHAT IS IN THIS FILE
| Dashboard | Six numbers, four charts and the ten largest open risks.
| Setup | Review date, contingency, and the team and category lists.
| Register | Forty rows: sentence, kind, money, response, owner, date, status.
| History | One row per review, for the exposure trend.
EXPLAINED IN
Risk Topic 4 · Writing a risk as a sentence
Risk Topic 6 · Why the matrix misleads
Risk Topic 8 · Aleatory and epistemic uncertainty
Risk Topic 13 · Response strategies
Example: the fourteen risks of the example project. Total expected value $99,730; nine epistemic risks carry $63,880 and about $9,300 would resolve all nine; five cost nothing; response spend $14,700; contingency $47,553. These are the lessons’ figures. The rock sentence is Risk Topic 4’s; the other sentences, the due dates and the response statuses are illustrative. Probability and impact are shown where the lessons give them; elsewhere the expected value is typed in and carries a note.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Risk register | [6 empty] | The Project Control Hub
Example project · Review 3 · 13 Mar 2026 · Project controls
TOTAL EXPECTED VALUE | EPISTEMIC · BUY INFORMATION |  | FREE TO RESOLVE |  | RESPONSE SPEND | CONTINGENCY CARRIED |  | RESPONSES OVERDUE | Chart data (formulas)
99730 | 63880 |  | 5 |  | 14700 | 47553 |  | 2 | Top 10 by expected value
[9 empty] | Rock in the pile bores | 24000
across 14 open risks | 9 risks · $9,300 to find out |  | epistemic risks: send the emails |  | 13 priced · 1 done | 48% of the expected value |  | 1 open risk(s) with no owner | Steel escalation | 15000
[9 empty] | Late detailing | 11000
[9 empty] | Wayleave unconfirmed | 8500
The one question for every line: if I spent money finding out, would the uncertainty get smaller? Yes → epistemic: buy information. No → aleatory: hold money. | [8 empty] | Groundwater in February | 7200
[9 empty] | Supplier insolvency | 6900
WHERE THE MONEY IS | [8 empty] | Long-lead switchgear | 6600
[9 empty] | Winter shutdown | 4000
[9 empty] | Waterproofing interface | 3510
[9 empty] | Crane breakdown | 3450
Expected value by kind
[9 empty] | Epistemic | 63880
[9 empty] | Aleatory | 24850
[9 empty] | Mixed | 11000
Epistemic: expected value against cost to find out
[9 empty] | Risk | Expected value | Cost to find out
[9 empty] | Rock in the pile bores | 24000 | 6800
[9 empty] | Groundwater in February | 7200 | 900
[9 empty] | Wayleave unconfirmed | 8500 | 0
[9 empty] | Supplier insolvency | 6900 | 200
[9 empty] | Long-lead switchgear | 6600 | 0
[9 empty] | Discharge consent | 1840 | 1400
BUY INFORMATION OR HOLD MONEY | [8 empty] | Waterproofing interface | 3510 | 0
[9 empty] | Temporary water | 1890 | 0
[9 empty] | Temporary power | 3440 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
THE TEN LARGEST OPEN RISKS
Risk |  | Kind | EV ($) | Response | Owner | Due | Response status | Overdue
Rock in the pile bores |  | Epistemic | 24000 | Investigate | Engineer | 2026-03-20 | In progress
Steel escalation |  | Aleatory | 15000
Late detailing |  | Mixed | 11000 | Reduce | Design manager | 2026-03-12 | In progress | 1
Wayleave unconfirmed |  | Epistemic | 8500 | Escalate | Commercial | 2026-03-14 | In progress
Groundwater in February |  | Epistemic | 7200 | Investigate | Engineer | 2026-03-27 | Not started
Supplier insolvency |  | Epistemic | 6900 | Reduce | Buyer | 2026-03-13 | Done
Long-lead switchgear |  | Epistemic | 6600 | Reduce | Buyer | 2026-03-11 | In progress | 2
Winter shutdown |  | Aleatory | 4000 | Accept | Planner
Waterproofing interface |  | Epistemic | 3510 | Investigate | QS | 2026-03-18 | Not started
Crane breakdown |  | Aleatory | 3450 | Accept | Site manager
Everything on this page reads from the Register. A red Owner cell is an open risk with nobody against it.

## Setup
Setup |  | The Project Control Hub
The review date, the contingency you carry, and the lists the register uses.
Change the review date at every review. Overdue responses are counted against it.
Project | Example project
Review number | 3
Review date (as at) | 2026-03-13
Contingency carried ($) | 47553 | Risk Topic 1: the 5% rule gave $47,553.
Prepared by | Project controls
Team (Owner drop-down) |  | Categories (Category drop-down)
| Project manager | Ground
| Engineer | Design
| Design manager | Procurement
| Planner | Commercial
| Buyer | Permits
| Commercial | Site services
| QS | Weather
| Site manager | Plant
Ahmet

## Register
Risk register | [21 empty] | The Project Control Hub
One risk per row, written as a sentence, priced in money, with one person against the response.
The test for Kind: if you spent money finding out, would the uncertainty get smaller? Yes = Epistemic. No = Aleatory.
ID | Risk | Because… (a fact today) | …may occur (the uncertain event) | …which would lead to (the effect) | Sentence | Category | Kind | Probability | Impact ($) | Expected value ($) | Cost to find out ($) | Value of finding out | Response | Response action | Response cost ($) | Owner | Due | Response status | Closes when | Risk status | Days overdue | Note | r | e
R01 | Rock in the pile bores | the ground investigation covered five boreholes on a forty-two pile site | rock may be encountered below pile toe level away from the tested locations | a heavier rig, two more days per affected bore and a delayed pile cap sequence | ✔ complete | Ground | Epistemic | 40% | 60000 | 24000 | 6800 | 3.5294 | Investigate | Drill two boreholes in the north half | 6800 | Engineer | 2026-03-20 | In progress | The last bore is drilled | Open |  |  | 1 | 1
R02 | Groundwater in February | the groundwater readings were taken in summer | groundwater may stand higher in the excavations in February | dewatering and slower excavation for the raft | ✔ complete | Ground | Epistemic |  |  | 7200 | 900 | 8 | Investigate | Take a winter standpipe reading | 900 | Engineer | 2026-03-27 | Not started | The raft excavation is backfilled | Open |  |  | 5 | 2
R03 | Wayleave unconfirmed | the access road crosses third-party land and no wayleave is signed | the landowner may refuse or delay access | deliveries without a road and a longer haul route | ✔ complete | Permits | Epistemic |  |  | 8500 | 0 | Free: ask | Escalate | Issue the wayleave letter (Ahmet) | 0 | Commercial | 2026-03-14 | In progress | The first lorry drives onto site | Open |  |  | 4 | 3
R04 | Supplier insolvency | the steel supplier is small and had not been credit checked | the supplier may fail before delivery | a re-order at a higher price and a gap in deliveries | ✔ complete | Commercial | Epistemic |  |  | 6900 | 200 | 34.5 | Reduce | Credit check the supplier | 600 | Buyer | 2026-03-13 | Done | The last steel is delivered | Open |  |  | 6 | 4
R05 | Long-lead switchgear | the switchgear lead time has only been quoted verbally | delivery may come later than energisation needs | a late energisation and standing time at the end | ✔ complete | Procurement | Epistemic |  |  | 6600 | 0 | Free: ask | Reduce | Order early and confirm the lead time in writing | 3200 | Buyer | 2026-03-11 | In progress | The switchgear is on site | Open | 2 |  | 7 | 5
R06 | Discharge consent | no pre-application enquiry has been made | the discharge consent may be refused or conditioned | redesigned drainage and a later connection | ✔ complete | Permits | Epistemic |  |  | 1840 | 1400 | 1.3143 | Reduce | Send the pre-application enquiry | 1400 | Engineer | 2026-03-20 | Not started | Consent is granted | Open |  |  | 14 | 6
R07 | Waterproofing interface | the drawings do not say who laps the membrane at the raft edge | the interface may be built twice or not at all | rework and a leak path at the raft edge | ✔ complete | Design | Epistemic |  |  | 3510 | 0 | Free: ask | Investigate | Send one clarification to the designer | 0 | QS | 2026-03-18 | Not started | The clarification is answered | Open |  |  | 9 | 7
R08 | Temporary water | the contract is silent on who provides temporary water | the client may not provide it | a temporary supply at our cost | ✔ complete | Site services | Epistemic |  |  | 1890 | 0 | Free: ask | Investigate | One email to the client | 0 | QS | 2026-03-18 | Not started | The client answers | Open |  |  | 13 | 8
R09 | Temporary power | the contract is silent on who provides temporary power | the client may not provide it | generators at our cost | ✔ complete | Site services | Epistemic |  |  | 3440 | 0 | Free: ask | Escalate | One email to the client | 0 | Commercial | 2026-03-20 | Not started | The client answers | Open |  |  | 11 | 9
R10 | Late detailing | the drawings are still at revision B | reinforcement details may arrive after the steel is due on site | idle gangs, rework and late pours | ✔ complete | Design | Mixed | 55% | 20000 | 11000 |  |  | Reduce | Issue the bar schedule revision | 0 | Design manager | 2026-03-12 | In progress | The last bar schedule is issued | Open | 1 |  | 3
R11 | Steel escalation | the steel order is not yet placed at a fixed price | the steel index may rise before the order | a higher price for the remaining tonnage | ✔ complete | Commercial | Aleatory | 50% | 30000 | 15000 | [8 empty] | The order is signed at a fixed price | Open |  |  | 2
R12 | Winter shutdown | the raft pours fall in January and February | frost may stop concreting for days at a time | lost working days and protection costs | ✔ complete | Weather | Aleatory |  |  | 4000 |  |  | Accept | Hold in contingency | 0 | Planner |  |  | The raft pours are complete | Open |  |  | 8
R13 | Crane breakdown | the job relies on a single crane | the crane may break down during a critical lift period | standing gangs and a hired replacement | ✔ complete | Plant | Aleatory |  |  | 3450 |  |  | Accept | Hold in contingency | 0 | Site manager |  |  | The crane is demobilised | Open |  |  | 10
R14 | Pump failure | every pour relies on one concrete pump | the pump may fail during a pour | a cold joint, rework and a lost pour ($12,000) | ✔ complete | Plant | Aleatory |  |  | 2400 |  |  | Reduce | Standby pump on pour days | 1800 | Site manager | 2026-03-27 | Not started | The last pour is complete | Open |  |  | 12
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
Summary
| Open risks |  |  | 14
| Total expected value ($) |  |  | 99730
| epistemic ($) |  |  | 63880
| aleatory ($) |  |  | 24850
| mixed ($) |  |  | 11000
| Epistemic risks |  |  | 9
| Cost to resolve the epistemic risks ($) |  |  | 9300
| Epistemic risks that cost nothing to resolve |  |  | 5
| Total response spend ($) |  |  | 14700
| Responses priced |  |  | 13
| Responses done |  |  | 1
| Open risks with no owner |  |  | 1
| Responses overdue |  |  | 2
| Sentences incomplete |  |  | 0
Note on K8: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K9: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K10: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K11: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K12: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K13: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K14: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K15: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on N17: No response in Risk Topic 13. Steel escalation is decided by the order: it dies when the order is signed at a fixed price. Until then it needs an owner.
Note on K18: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K19: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.
Note on K20: Expected value as stated in Risk Topic 8. The lessons do not give this risk a separate probability and impact, so it is typed in. Fill Probability and Impact and it calculates.

## History
History | [6 empty] | The Project Control Hub
One row per review, so the trend is visible: is the register getting shorter and cheaper?
At each review: copy the blue "This review" row and Paste Special → Values into the next empty row.
This review (live)
3 | 2026-03-13 | 14 | 99730 | 63880 | 24850 | 47553 | 14700
Review | Date | Open risks | Total EV ($) | Epistemic EV ($) | Aleatory EV ($) | Contingency ($) | Response spend ($)
1 | 2026-01-16 | 5 | 51400 |  |  | 47553
2 | 2026-02-13 | 14 | 99730 | 63880 | 24850 | 47553
3 | 2026-03-13 | 14 | 99730 | 63880 | 24850 | 47553 | 14700
Note on D8: Risk Topic 1: the first five-line register added up to $51,400.
Note on C9: Risk Topic 4: twenty-two candidates, eight of them not risks, fourteen left.