## Start
Schedule update checklist
Keep the model honest while ten thousand things try to make it lie. Then report.
The Project Control Hub · free template
EVERY PERIOD, SAME DAY, SAME RULES · analyse, then act, then report
1 | Updates → | Add this update’s line: data date, the scheduling option, the forecast finish. Set its number in Setup. | 2 minutes
2 | Remaining days → | Every started activity: "how many days do you still need?" Write who said it and from which record. | 15 minutes
3 | Health check → | The ten-minute check: count open ends, hard constraints, negative and huge float, long lags, out-of-sequence work. | 10 minutes
4 | Float trend → | The float of your top ten activities. The sheet reads the slope and says when each one runs out. | 5 minutes
5 | Actions → | Every slipping path: an action, a person and a date. | 10 minutes
6 | Checklist → | Work down the list. The verdict turns green when every must-do line is done. Then write the report. | 10 minutes
ASK THE OTHER QUESTION
| "How far along are you?" | "About ninety percent." He said that last month too. Percent complete looks backwards.
| "How many days left?" | "Eight. We are waiting on the glass." Now you have a forecast, and a reason you can go and fix.
THREE PLACES THE ROT HIDES · Topic 17
| Progress override | The default in most tools. Drops the logic when the site builds out of order. The finish is early, and fiction. Use retained logic.
| A hard constraint | Does not protect the date. It protects you from hearing about it: the delay arrives and the float still says zero.
| An open end | Nothing to push against, so the software hands out 180 days of imaginary float. Huge float is a broken gauge.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in: Setup, Updates, Remaining days, Health check, Float trend, Actions, and Status in the Checklist.
| White, black text | A formula. Leave it alone and it keeps working. The Dashboard is all formulas.
| Red | A must-do line still open, negative float, a finish that moved, a path without an owner.
WHAT IS IN THIS FILE
| Dashboard | The verdict, seven numbers, a paragraph, what is open, the float radar and three charts.
| Checklist | 29 lines in seven steps, each with why it matters and what the file shows.
| Health check | Eight counts per update, against a target, with the action for each.
| Float trend | Twenty activities, twelve updates: change, burn per update, when it runs out.
| Remaining days | Days left from site, with the source, stuck percentages and finishes that moved.
| Actions | Every slipping path: action, owner, date, and what is missing.
| Updates | One line per update: data date, scheduling option, forecast finish, why it moved.
| Setup | This update’s number, the contract date, the limits and the drop-down lists.
EXPLAINED IN
Schedule Topic 16 · Keeping the model honest
Schedule Topic 17 · Updated perfectly, completely wrong
Blank: twelve updates, twenty activities on the float trend, forty in Remaining days and thirty actions ready to fill. Start with update 1 in Updates. The example file shows update six of the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Schedule update | [7 empty] | The Project Control Hub
CHECKLIST |  | HEALTH CHECKS FAILING | FORECAST FINISH |  | LATE AGAINST CONTRACT |  | ALREADY LATE | PATHS WITHOUT AN OWNER | REMAINING-DAYS FLAGS
BEFORE YOU ISSUE · open lines, must-do first
No. | Check |  |  |  | Must | Status | Owner | Evidence / note
THE FLOAT RADAR · lowest float first
Activity |  |  |  | Float now | Change | Burn / upd. | Reading
THE SLOPE, NOT THE VALUE
Lines above 60 days are cut off: anything that high belongs in the Health check, not on this chart. The finish chart shows the forecast finish minus the contract date in Setup.
Everything on this page reads from Setup, Updates, Checklist, Health check, Float trend, Remaining days and Actions.

## Checklist
Checklist | [7 empty] | The Project Control Hub
Collect, enter, recalculate, check, analyse, act: then report. Same day, same rules, every period.
Set the Status of each line. "What the file shows" reads the other sheets so you are not ticking from memory.
No. | Check | Why it matters | Must | What the file shows | Status | Evidence / note | Owner | Lesson | Sort key
1 · COLLECT · before you open the software
1.1 | Same cut-off day and the same rules as every update | A schedule updated when someone remembers is not a control system. | Must |  |  |  |  | Topic 16
1.2 | Actual dates from site records: diary, inspection sheets, delivery notes | An actual invented in a car anchors every forecast downstream of it. | Must |  |  |  |  | Topic 16
1.3 | Every started activity asked "how many days do you still need?" | Percent complete looks backwards. Remaining duration is the only number that can move a date. | Must |  |  |  |  | Topic 16
1.4 | No percentage taken from a phone call; stuck percentages challenged | Ninety percent for three months is not ninety percent complete. It is a problem nobody has described. | [5 empty] | Topic 16
1.5 | Subcontractor programmes received, and their scheduling option checked | If they run progress override, they have been sending you optimistic fiction. | [5 empty] | Topic 16
2 · ENTER
2.1 | Data date moved to the cut-off | Everything before it is history, everything after it is forecast. | Must |  |  |  |  | Topic 16
2.2 | Actual starts and finishes entered for everything that moved | An activity that finished on site but not in the model keeps pushing its successors. | [5 empty] | Topic 16
2.3 | No actual date later than the data date | An actual in the future is a typing error, never progress. | Must |  |  |  |  | Topic 16
2.4 | Remaining durations entered, not only percent complete | The software forecasts from remaining duration. | [5 empty] | Topic 16
3 · RECALCULATE
3.1 | Scheduling option set to retained logic, not progress override | Override deletes real dependencies and returns a date that is not real. | Must |  |  |  |  | Topic 17
3.2 | Recalculated and saved as a new version; last update kept to compare | Without last month’s file there is no trend. | [5 empty] | Topic 17
3.3 | Baseline untouched | Re-baselining without an approved change hides the slip you are meant to report. | [5 empty] | Topic 17
4 · HEALTH CHECK · ten minutes, before a word of the report
4.1 | No open ends, apart from the first and the last activity | An open end has nothing to push against, so it hands out imaginary float. | Must |  |  |  |  | Topic 17
4.2 | Every hard constraint justified in writing; none absorbing a delay | A hard constraint does not protect the date. It protects you from hearing about it. | Must |  |  |  |  | Topic 17
4.3 | Out-of-sequence progress reviewed, logic corrected where the site changed the order | The default setting throws away the logic you spent weeks building. | [5 empty] | Topic 17
4.4 | Unusually large float investigated, not reported as good news | Treat it like a pressure gauge reading zero: a broken instrument. | [5 empty] | Topic 17
4.5 | Long lags turned into activities with an owner | Waiting that belongs to a person should have their name on it. | [5 empty] | Topic 17
5 · ANALYSE
5.1 | Float on the top ten compared with last update: the change, not the value | Today’s float says where you stand. The slope says where you are going. | Must |  |  |  |  | Topic 16
5.2 | Every activity burning float named, with when it runs out | The facade burns five days a month. In January it looked green; the trend already knew. | [5 empty] | Topic 16
5.3 | Every activity with negative float listed as already late | Negative float is not a warning that you might be late. You are. | Must |  |  |  |  | Topic 16
5.4 | Forecast finish compared with last update and with the contract; every move explained | A finish that moves without a reason is a finish nobody understands. | Must |  |  |  |  | Topic 16
5.5 | Delay stated in time as well as money | Earned schedule turns the cost report into months behind (Earned value calculator). | [5 empty] | Topic 16
6 · ACT
6.1 | Every slipping path has an action, a person and a date | Analysis that ends without an owner is project journalism. | Must |  |  |  |  | Topic 16
6.2 | Recovery options tested in a copy, not in the live update | The update records what is true; the copy tests what could be. | [5 empty] | Topic 16
6.3 | Decisions needed from the client written as requests, with a date | A decision nobody asked for in writing is a decision nobody owes you. | [5 empty] | Topic 16
7 · REPORT · last, not instead
7.1 | Report written after the analysis, not instead of it | Reporting without analysis is describing the accident instead of steering away from it. | Must |  |  |  |  | Topic 16
7.2 | First paragraph: how far the finish moved, why, and what is being done | Most readers stop after the first paragraph. | [5 empty] | Topic 16
7.3 | Issued on the same working day after the cut-off as every period | A late report is read as a hidden problem. | [5 empty] | Topic 16
7.4 | Schedule file, this checklist and the report archived together | Next month’s comparison starts here. | [5 empty] | Topic 16
Done: checked, nothing wrong · Fixed: found and corrected · Open: found, not corrected · Not done: not checked yet · N/A. Must-do lines need Done or Fixed.

## Health check
Health check | [17 empty] | The Project Control Hub
The ten-minute check, every update, before a word of the report. Count what you find.
Type the count for each update in its column. Nobody has ever run this list on a live project and found nothing.
Check | How to find it | U1 | U2 | U3 | U4 | U5 | U6 | U7 | U8 | U9 | U10 | U11 | U12 | This update | Last update | Change | Target | Result
Open ends | Activities with no predecessor or no successor, apart from the first and the last. In P6: filter on predecessors / successors empty. | [15 empty] | 0
Hard constraints without a written reason | "Must finish on", "mandatory start / finish" and the like, with no note saying why. Each one stops a delay from travelling. | [15 empty] | 0
Activities with negative float | Total float below zero. The deadline has already passed the work. | [15 empty] | 0
Float above the Setup limit | Total float above the "suspicious" value in Setup. Usually a missing link, not good news. | [15 empty] | 0
Lags longer than the Setup limit | Long lags hide work that belongs to somebody: curing, approvals, deliveries. | [15 empty] | 0
Out-of-sequence progress | Started before its predecessor finished. Override drops the logic; retained logic keeps it. | [15 empty] | 0
Actual dates after the data date | An actual start or finish in the future. Always a typing error, never progress. | [15 empty] | 0
Started activities with no remaining duration from site | Anything in progress where nobody was asked "how many days do you still need?" | [15 empty] | 0
FOUND THIS UPDATE
The limits for "suspicious float" and "long lags" are in Setup. The highlighted column is the update in Setup. Retained logic or progress override is recorded per update in Updates.

## Float trend
Float trend | [20 empty] | The Project Control Hub
Float is a radar, not a number: the change since last update, and the update it runs out.
Type the total float of your ten (or twenty) most important activities at every update. Read the slope, not the value.
ID | Activity | U1 | U2 | U3 | U4 | U5 | U6 | U7 | U8 | U9 | U10 | U11 | U12 | Path | Float now | Last update | Change | Burn per update | Runs out in (updates) | Reading | Note | Sort key
Burn per update = the float lost per update over the window in Setup. "Runs out in" divides the float left by that burn. The highlighted column is the update in Setup.

## Remaining days
Remaining days | [11 empty] | The Project Control Hub
Ask "how many days do you still need?", not "how far along are you?".
One line per started activity. Write who gave the figure and from which record. The flags fill themselves.
P6 ID | Activity | Who gave the figure | Source | % two updates ago | % last update | % now | Days left, last update | Days left, now | Should be left now | Finish moved (working days) | Cause: what are they waiting for? | Flag | ✔
"Should be left now" takes the working days since the last update (Setup) off last update’s figure. Finish moved = days left now minus that (it can be more than the period when work stood still).

## Actions
Actions | [7 empty] | The Project Control Hub
Every slipping path ends in a person and a date. Analysis without an owner is project journalism.
One line per slipping path. The flag says what is missing.
Slipping path / activity | How bad | Action | Owner | Due | Status | Done on | Days to due | Flag
Days to due count from the data date of the update in Setup.

## Updates
Updates | [10 empty] | The Project Control Hub
One line per update: the data date, the setting, the forecast finish and why it moved.
Add the line before you start the checklist. The finish movement and the health counts work themselves out.
Update | Data date | Same cut-off rule? | Scheduling option | Forecast finish | Days late vs contract | Moved since last update (days) | Health checks failing | Activities with negative float | Issued on | Working days to issue | Why the finish moved
1
2
3
4
5
6
7
8
9
10
11
12
The row with the teal border is the update in Setup. Days are calendar days; working days to issue count from the data date.
Formulas:
Working days to issue = IF(OR([Data date]="",[Issued on]=""),"",NETWORKDAYS([Data date],[Issued on])-1)

## Setup
Setup |  |  |  |  | The Project Control Hub
Which update this is, the contract date, and the limits the health check uses.
Change the update number every period, after you add its line in Updates. Everything else reads from here.
Project
This update (number) | 1 | The row in Updates that this checklist is for.
Data date (from Updates) |  | Type it in Updates, on the row of this update.
Contract completion date |  | The date the forecast finish is measured against.
Cut-off rule | Last working day of the month | Same day, same rules, every period (Topic 16).
Float this high is suspicious (days) | 100 | Pick a value well above any honest float on your job. Topic 17: 180 days on temporary works is a missing link.
Lags longer than this need an owner (days) | 10 | Curing can be a lag. An approval cannot.
Measure the float burn over (updates) | 3 | The slope is the average loss per update over this many updates.
Warn when float runs out within (updates) | 3 | Turns the Float trend amber before it turns red.
Scheduling software | Primavera P6
Working days since the last update |  | The Remaining days sheet uses it to see whether a finish moved.
LISTS · the drop-downs read from here
Status |  |  | Source of the figure | Owners (roles) | Scheduling option
Done |  |  | Site diary | Planner | Retained logic
Fixed |  |  | Inspection sheet | Project manager | Progress override
Open |  |  | Delivery note | Site manager | Actual dates
Not done |  |  | Survey | Site engineer
N/A |  |  | Timesheet | Engineer
|  |  | Test certificate | Design manager
|  |  | Phone call | Buyer
|  |  | Memory | Commercial
Piling sub
Concrete sub
Rebar sub
Groundworks
Electrical sub
Status: Done = checked, nothing wrong. Fixed = something was wrong and is now corrected. Open = found, not yet corrected. Not done = not checked yet. Must-do items need Done or Fixed before the update goes out.