## Start
Schedule update checklist
Keep the model honest while ten thousand things try to make it lie. Then report.
The Project Control Hub · free template · example: update six of the example project
EVERY PERIOD, SAME DAY, SAME RULES · analyse, then act, then report
1 | Updates → | Add this update’s line: data date, the scheduling option, the forecast finish. Set its number in Setup. | 2 minutes
2 | Remaining days → | Every started activity: "how many days do you still need?" Write who said it and from which record. | 15 minutes
3 | Health check → | The ten-minute check: count open ends, hard constraints, negative and huge float, long lags, out-of-sequence work. | 10 minutes
4 | Float trend → | The float of your top ten activities. The sheet reads the slope and says when each one runs out. | 5 minutes
5 | Actions → | Every slipping path: an action, a person and a date. | 10 minutes
6 | Checklist → | Work down the list. The verdict turns green when every must-do line is done. Then write the report. | 10 minutes
ASK THE OTHER QUESTION
| "How far along are you?" | "About ninety percent." He said that last month too. Percent complete looks backwards.
| "How many days left?" | "Eight. We are waiting on the glass." Now you have a forecast, and a reason you can go and fix.
THREE PLACES THE ROT HIDES · Topic 17
| Progress override | The default in most tools. Drops the logic when the site builds out of order. The finish is early, and fiction. Use retained logic.
| A hard constraint | Does not protect the date. It protects you from hearing about it: the delay arrives and the float still says zero.
| An open end | Nothing to push against, so the software hands out 180 days of imaginary float. Huge float is a broken gauge.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in: Setup, Updates, Remaining days, Health check, Float trend, Actions, and Status in the Checklist.
| White, black text | A formula. Leave it alone and it keeps working. The Dashboard is all formulas.
| Red | A must-do line still open, negative float, a finish that moved, a path without an owner.
WHAT IS IN THIS FILE
| Dashboard | The verdict, seven numbers, a paragraph, what is open, the float radar and three charts.
| Checklist | 29 lines in seven steps, each with why it matters and what the file shows.
| Health check | Eight counts per update, against a target, with the action for each.
| Float trend | Twenty activities, twelve updates: change, burn per update, when it runs out.
| Remaining days | Days left from site, with the source, stuck percentages and finishes that moved.
| Actions | Every slipping path: action, owner, date, and what is missing.
| Updates | One line per update: data date, scheduling option, forecast finish, why it moved.
| Setup | This update’s number, the contract date, the limits and the drop-down lists.
EXPLAINED IN
Schedule Topic 16 · Keeping the model honest
Schedule Topic 17 · Updated perfectly, completely wrong
Example: update six of the example project, data date Tuesday 30 June 2026. The update switches the scheduling option from progress override to retained logic and takes the must-finish-on off the substation slab: the finish moves 21 days later and the slab shows -10 days of float. It stopped hiding. The switchgear has lost five days of float every update and is now four days late. Two slipping paths have no owner, so the update is not ready to issue. The rock, the raft rebar and the switchgear lead time are the example project’s; the floats, counts and dates are illustrative.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Schedule update | [7 empty] | The Project Control Hub
Example project · update 6 · data date 30 Jun 2026 · Retained logic
NOT READY TO ISSUE · 1 must-do item(s) still open
CHECKLIST |  | HEALTH CHECKS FAILING | FORECAST FINISH |  | LATE AGAINST CONTRACT |  | ALREADY LATE | PATHS WITHOUT AN OWNER | REMAINING-DAYS FLAGS
23 |  | 6 | 2026-09-04 |  | 42 |  | 2 | 2 | 7
of 29 lines · 6 open |  | of 8 · 12 items found | +21 days since last update |  | days after 24 Jul 2026 |  | activities with negative float · 4 running out | 0 action(s) overdue | of 12 started activities
The finish is forecast for 4 September 2026, 42 days against the contract. 2 activities are already late and 4 will run out of float within 3 updates. The health check found 12 items. 2 slipping path(s) still have no owner.
BEFORE YOU ISSUE · open lines, must-do first
No. | Check |  |  |  | Must | Status | Owner | Evidence / note
6.1 | Every slipping path has an action, a person and a date |  |  |  | Must | Not done | Project manager | Two paths still without an owner
1.4 | No percentage taken from a phone call; stuck percentages challenged |  |  |  |  | Open | Site engineer | Earthing came by phone. Switchgear and the outfall stuck: causes written down
4.4 | Unusually large float investigated, not reported as good news |  |  |  |  | Open | Planner | Temporary compound removal, 180 days: linked only to the finish
4.5 | Long lags turned into activities with an owner |  |  |  |  | Open | Planner | Three over 10 days. Two are curing; one is an approval
7.3 | Issued on the same working day after the cut-off as every period |  |  |  |  | Not done | Planner
7.4 | Schedule file, this checklist and the report archived together |  |  |  |  | Not done | Planner
THE FLOAT RADAR · lowest float first
Activity |  |  |  | Float now | Change | Burn / upd. | Reading
Substation slab |  |  |  | -10 | -10 | 3.3333 | Already late by 10 days
Switchgear delivery and installation |  |  |  | -4 | -5 | 4.3333 | Already late by 4 days
Raft concrete pours |  |  |  | 2 | -2 | 1.3333 | Runs out in about 2 update(s) at this rate
Testing and commissioning |  |  |  | 2 | -4 | 2 | Runs out in about 1 update(s) at this rate
Drainage connection to the outfall |  |  |  | 3 | -22 | 8.3333 | Runs out in about 1 update(s) at this rate
Handover documents |  |  |  | 6 | -4 | 2 | Runs out in about 3 update(s) at this rate
Cable pulling and terminations |  |  |  | 8 | -2 | 2.3333 | Burning 2.3 days an update
Earthing and lightning protection |  |  |  | 16 | -2 | 2 | Burning 2.0 days an update
Boundary fence and gates |  |  |  | 36 | -2 | 1.3333 | Burning 1.3 days an update
Temporary compound removal |  |  |  | 180 | 0 | 0 | Suspicious: 180 days is a missing link, not good news
THE SLOPE, NOT THE VALUE
Lines above 60 days are cut off: anything that high belongs in the Health check, not on this chart. The finish chart shows the forecast finish minus the contract date in Setup.
Everything on this page reads from Setup, Updates, Checklist, Health check, Float trend, Remaining days and Actions.

## Checklist
Checklist | [7 empty] | The Project Control Hub
Collect, enter, recalculate, check, analyse, act: then report. Same day, same rules, every period.
Set the Status of each line. "What the file shows" reads the other sheets so you are not ticking from memory.
NOT READY TO ISSUE · 1 must-do item(s) still open | [8 empty] | 1
No. | Check | Why it matters | Must | What the file shows | Status | Evidence / note | Owner | Lesson | Sort key
1 · COLLECT · before you open the software
1.1 | Same cut-off day and the same rules as every update | A schedule updated when someone remembers is not a control system. | Must | Same rule: Last working day of the month | Done | Last working day of June, as every month | Planner | Topic 16
1.2 | Actual dates from site records: diary, inspection sheets, delivery notes | An actual invented in a car anchors every forecast downstream of it. | Must | 1 figure(s) from a phone call or memory | Done | All actual dates from the daily reports. The one phone-call figure (earthing) is a percentage, not an actual date: see 1.4 | Planner | Topic 16
1.3 | Every started activity asked "how many days do you still need?" | Percent complete looks backwards. Remaining duration is the only number that can move a date. | Must | 12 in Remaining days, 0 without days left | Done | Twelve activities asked, in the Remaining days sheet | Planner | Topic 16
1.4 | No percentage taken from a phone call; stuck percentages challenged | Ninety percent for three months is not ninety percent complete. It is a problem nobody has described. |  | 2 stuck, 1 not from a record | Open | Earthing came by phone. Switchgear and the outfall stuck: causes written down | Site engineer | Topic 16 | 1011
1.5 | Subcontractor programmes received, and their scheduling option checked | If they run progress override, they have been sending you optimistic fiction. |  |  | Done | Piling and electrical programmes in; both on retained logic | Planner | Topic 16
2 · ENTER
2.1 | Data date moved to the cut-off | Everything before it is history, everything after it is forecast. | Must | Data date 30 Jun 2026 | Done |  | Planner | Topic 16
2.2 | Actual starts and finishes entered for everything that moved | An activity that finished on site but not in the model keeps pushing its successors. |  |  | Done |  | Planner | Topic 16
2.3 | No actual date later than the data date | An actual in the future is a typing error, never progress. | Must | 0 found | Done | None found | Planner | Topic 16
2.4 | Remaining durations entered, not only percent complete | The software forecasts from remaining duration. |  |  | Done |  | Planner | Topic 16
3 · RECALCULATE
3.1 | Scheduling option set to retained logic, not progress override | Override deletes real dependencies and returns a date that is not real. | Must | Retained logic | Fixed | Was progress override since update 1. Switched: the finish moved 21 days | Planner | Topic 17
3.2 | Recalculated and saved as a new version; last update kept to compare | Without last month’s file there is no trend. |  |  | Done | Saved as update 6; update 5 kept | Planner | Topic 17
3.3 | Baseline untouched | Re-baselining without an approved change hides the slip you are meant to report. |  |  | Done |  | Planner | Topic 17
4 · HEALTH CHECK · ten minutes, before a word of the report
4.1 | No open ends, apart from the first and the last activity | An open end has nothing to push against, so it hands out imaginary float. | Must | 2 found | Fixed | Two found and linked. The compound removal: see 4.4 | Planner | Topic 17
4.2 | Every hard constraint justified in writing; none absorbing a delay | A hard constraint does not protect the date. It protects you from hearing about it. | Must | 1 found | Fixed | Must-finish-on taken off the substation slab: float -10 | Planner | Topic 17
4.3 | Out-of-sequence progress reviewed, logic corrected where the site changed the order | The default setting throws away the logic you spent weeks building. |  | 3 found | Fixed | Three found; logic corrected by hand on all three | Planner | Topic 17
4.4 | Unusually large float investigated, not reported as good news | Treat it like a pressure gauge reading zero: a broken instrument. |  | 1 found | Open | Temporary compound removal, 180 days: linked only to the finish | Planner | Topic 17 | 1026
4.5 | Long lags turned into activities with an owner | Waiting that belongs to a person should have their name on it. |  | 3 found | Open | Three over 10 days. Two are curing; one is an approval | Planner | Topic 17 | 1027
5 · ANALYSE
5.1 | Float on the top ten compared with last update: the change, not the value | Today’s float says where you stand. The slope says where you are going. | Must | 10 compared; worst change -22 days | Done | Ten compared in the Float trend sheet | Planner | Topic 16
5.2 | Every activity burning float named, with when it runs out | The facade burns five days a month. In January it looked green; the trend already knew. |  | 4 run out within 3 updates | Done | Raft pours, commissioning, handover and the outfall named | Planner | Topic 16
5.3 | Every activity with negative float listed as already late | Negative float is not a warning that you might be late. You are. | Must | 2 with negative float | Done | Switchgear 4 days, substation slab 10 days | Planner | Topic 16
5.4 | Forecast finish compared with last update and with the contract; every move explained | A finish that moves without a reason is a finish nobody understands. | Must | Finish 4 Sep 26 · moved +21 d | Done | Retained logic and the slab constraint: 21 days | Planner | Topic 16
5.5 | Delay stated in time as well as money | Earned schedule turns the cost report into months behind (Earned value calculator). |  |  | Done |  | Commercial | Topic 16
6 · ACT
6.1 | Every slipping path has an action, a person and a date | Analysis that ends without an owner is project journalism. | Must | 2 path(s) without an owner | Not done | Two paths still without an owner | Project manager | Topic 16 | 35
6.2 | Recovery options tested in a copy, not in the live update | The update records what is true; the copy tests what could be. |  |  | Done | Two-gang slab option tested in a copy: 6 of the 10 days back | Planner | Topic 16
6.3 | Decisions needed from the client written as requests, with a date | A decision nobody asked for in writing is a decision nobody owes you. |  |  | N/A | None needed this month |  | Topic 16
7 · REPORT · last, not instead
7.1 | Report written after the analysis, not instead of it | Reporting without analysis is describing the accident instead of steering away from it. | Must |  | Done | Draft written after the float review; not issued | Planner | Topic 16
7.2 | First paragraph: how far the finish moved, why, and what is being done | Most readers stop after the first paragraph. |  |  | Done |  | Planner | Topic 16
7.3 | Issued on the same working day after the cut-off as every period | A late report is read as a hidden problem. |  | Not issued yet | Not done |  | Planner | Topic 16 | 1041
7.4 | Schedule file, this checklist and the report archived together | Next month’s comparison starts here. |  |  | Not done |  | Planner | Topic 16 | 1042
Done: checked, nothing wrong · Fixed: found and corrected · Open: found, not corrected · Not done: not checked yet · N/A. Must-do lines need Done or Fixed.

## Health check
Health check | [17 empty] | The Project Control Hub
The ten-minute check, every update, before a word of the report. Count what you find.
Type the count for each update in its column. Nobody has ever run this list on a live project and found nothing.
Check | How to find it | U1 | U2 | U3 | U4 | U5 | U6 | U7 | U8 | U9 | U10 | U11 | U12 | This update | Last update | Change | Target | Result
Open ends | Activities with no predecessor or no successor, apart from the first and the last. In P6: filter on predecessors / successors empty. | U1: 4; U2: 3; U3: 3; U4: 2; U5: 2; U6: 2 | 2 | 2 | 0 | 0 | 2 found. Link it. Open ends make float out of nothing.
Hard constraints without a written reason | "Must finish on", "mandatory start / finish" and the like, with no note saying why. Each one stops a delay from travelling. | U1: 1; U2: 1; U3: 2; U4: 2; U5: 2; U6: 1 | 1 | 2 | -1 | 0 | 1 found. Write the reason or take it off.
Activities with negative float | Total float below zero. The deadline has already passed the work. | U1: 0; U2: 0; U3: 0; U4: 0; U5: 0; U6: 2 | 2 | 0 | 2 | 0 | 2 found. List them as late, with how late, in the report.
Float above the Setup limit | Total float above the "suspicious" value in Setup. Usually a missing link, not good news. | U1: 2; U2: 2; U3: 2; U4: 1; U5: 1; U6: 1 | 1 | 1 | 0 | 0 | 1 found. Investigate: find the missing successor.
Lags longer than the Setup limit | Long lags hide work that belongs to somebody: curing, approvals, deliveries. | U1: 5; U2: 5; U3: 4; U4: 4; U5: 3; U6: 3 | 3 | 3 | 0 | 0 | 3 found. Make it an activity with an owner.
Out-of-sequence progress | Started before its predecessor finished. Override drops the logic; retained logic keeps it. | U1: 0; U2: 2; U3: 3; U4: 5; U5: 4; U6: 3 | 3 | 4 | -1 | 0 | 3 found. Correct the logic by hand where the site changed the order.
Actual dates after the data date | An actual start or finish in the future. Always a typing error, never progress. | U1: 1; U2: 0; U3: 0; U4: 0; U5: 0; U6: 0 | 0 | 0 | 0 | 0 | ✔ clean
Started activities with no remaining duration from site | Anything in progress where nobody was asked "how many days do you still need?" | U1: 6; U2: 4; U3: 3; U4: 2; U5: 1; U6: 0 | 0 | 1 | -1 | 0 | ✔ clean
FOUND THIS UPDATE | 6 of 8 checks found something, 12 items in all. Fix them, or say in the report why they stay.
The limits for "suspicious float" and "long lags" are in Setup. The highlighted column is the update in Setup. Retained logic or progress override is recorded per update in Updates.

## Float trend
Float trend | [20 empty] | The Project Control Hub
Float is a radar, not a number: the change since last update, and the update it runs out.
Type the total float of your ten (or twenty) most important activities at every update. Read the slope, not the value.
ID | Activity | U1 | U2 | U3 | U4 | U5 | U6 | U7 | U8 | U9 | U10 | U11 | U12 | Path | Float now | Last update | Change | Burn per update | Runs out in (updates) | Reading | Note | Sort key
A13 | Switchgear delivery and installation | 24 | 18 | 9 | 5 | 1 | -4 | [6 empty] | Procurement | -4 | 1 | -5 | 4.3333 |  | Already late by 4 days | Five days an update, every update. In February it looked fine; the slope already knew. | -3.993
A11 | Substation slab | 18 | 18 | 0 | 0 | 0 | -10 | [6 empty] | Substation | -10 | 0 | -10 | 3.3333 |  | Already late by 10 days | Pinned by a must-finish-on from update 3 to 5. Taken off in update 6: the ten days were there all along. | -9.992
A10 | Raft concrete pours | 10 | 10 | 6 | 4 | 4 | 2 | [6 empty] | Substation | 2 | 4 | -2 | 1.3333 | 1.5 | Runs out in about 2 update(s) at this rate | Follows the raft rebar. | 2.009
A15 | Cable pulling and terminations | 20 | 20 | 15 | 12 | 10 | 8 | [6 empty] | Substation | 8 | 10 | -2 | 2.3333 | 3.4286 | Burning 2.3 days an update |  | 8.01
A16 | Testing and commissioning | 12 | 12 | 8 | 6 | 6 | 2 | [6 empty] | Substation | 2 | 6 | -4 | 2 | 1 | Runs out in about 1 update(s) at this rate |  | 2.011
A17 | Handover documents | 15 | 15 | 12 | 10 | 10 | 6 | [6 empty] | Site | 6 | 10 | -4 | 2 | 3 | Runs out in about 3 update(s) at this rate |  | 6.012
A18 | Earthing and lightning protection | 25 | 25 | 22 | 20 | 18 | 16 | [6 empty] | Site | 16 | 18 | -2 | 2 | 8 | Burning 2.0 days an update |  | 16.013
A19 | Drainage connection to the outfall | 30 | 30 | 28 | 26 | 25 | 3 | [6 empty] | Site | 3 | 25 | -22 | 8.3333 | 0.36 | Runs out in about 1 update(s) at this rate | Stuck at 90% for three updates, waiting for the discharge consent. This update the days left were asked for: -22. | 3.014
A20 | Boundary fence and gates | 40 | 40 | 40 | 38 | 38 | 36 | [6 empty] | Site | 36 | 38 | -2 | 1.3333 | 27 | Burning 1.3 days an update |  | 36.015
A21 | Temporary compound removal | 180 | 180 | 180 | 180 | 180 | 180 | [6 empty] | Site | 180 | 180 | 0 | 0 |  | Suspicious: 180 days is a missing link, not good news | Linked only to the finish milestone: 180 days of float nobody can use. | 180.016
Burn per update = the float lost per update over the window in Setup. "Runs out in" divides the float left by that burn. The highlighted column is the update in Setup.
Note on C7: Schedule Topic 16: five days of float lost every update. The weekly report shows the same activity week by week. Values are illustrative.

## Remaining days
Remaining days | [11 empty] | The Project Control Hub
Ask "how many days do you still need?", not "how far along are you?".
One line per started activity. Write who gave the figure and from which record. The flags fill themselves.
P6 ID | Activity | Who gave the figure | Source | % two updates ago | % last update | % now | Days left, last update | Days left, now | Should be left now | Finish moved (working days) | Cause: what are they waiting for? | Flag | ✔
A10 | Raft concrete pours, bay 3 | Site engineer | Site diary | 30% | 60% | 90% | 24 | 4 | 2 | 2 | Two pours left; cube results on the last. | Finish moved 2 working days later.
A13 | Switchgear delivery and installation | Buyer | Delivery note | 30% | 30% | 30% | 30 | 13 | 8 | 5 | "Eight more days of testing. We are waiting on the factory test certificate." | Stuck at 30% for three updates: describe the problem. Finish moved 5 working days later.
A15 | Cable pulling and terminations | Site engineer | Inspection sheet | 20% | 40% | 55% | 38 | 18 | 16 | 2 |  | Finish moved 2 working days later.
A18 | Earthing and lightning protection | Electrical sub | Phone call | 50% | 70% | 80% | 28 | 8 | 6 | 2 | "About eighty percent." Not yet checked against the inspection sheets. | Not a site record: check it. Finish moved 2 working days later.
A19 | Drainage connection to the outfall | Engineer | Site diary | 90% | 90% | 90% | 8 | 8 | 0 | 22 | "Eight days, once we have the consent." Ninety percent for three updates. | Stuck at 90% for three updates: describe the problem. Finish moved 22 working days later.
A12 | Drainage and ducts | Site engineer | Survey | 70% | 85% | 100% | 5 | 0 | 0 |  | Finished 24 June. |  | ✔
A20 | Boundary fence and gates | Groundworks | Site diary | 10% | 25% | 40% | 40 | 20 | 18 | 2 |  | Finish moved 2 working days later.
A22 | Access road surfacing | Groundworks | Delivery note | 0% | 30% | 75% | 26 | 4 | 4 | 0 |  |  | ✔
A23 | Transformer bund walls | Concrete sub | Inspection sheet | 0% | 20% | 45% | 32 | 12 | 10 | 2 | One wall re-poured after a failed cube. | Finish moved 2 working days later.
A24 | Control building fit-out | Electrical sub | Timesheet | 0% | 10% | 30% | 48 | 26 | 26 | 0 |  |  | ✔
A25 | Substation slab | Concrete sub | Site diary |  |  | 15% |  | 24 |  |  | Started 22 June after the raft bay 2 pour. |  | ✔
A26 | Landscaping | Groundworks | Site diary |  |  | 5% |  | 20 |  |  | Started 29 June. |  | ✔
"Should be left now" takes the working days since the last update (Setup) off last update’s figure. Finish moved = days left now minus that (it can be more than the period when work stood still).

## Actions
Actions | [7 empty] | The Project Control Hub
Every slipping path ends in a person and a date. Analysis without an owner is project journalism.
One line per slipping path. The flag says what is missing.
Slipping path / activity | How bad | Action | Owner | Due | Status | Done on | Days to due | Flag
Switchgear delivery and installation | 4 days late | Get the factory test date in writing; ask for a part delivery of the two incomers | Buyer | 2026-07-07 | Open |  | 7 | Open, on time
Substation slab | 10 days late | Second concrete gang for the slab; pour in two halves | Site manager | 2026-07-03 | Open |  | 3 | Open, on time
Testing and commissioning | 2 days float, burning 2 an update | Commission in two stages: incomers first |  | 2026-07-10 | Open |  | 10 | No owner: nobody will do it
Raft concrete pours | 2 days float | Book the pump for both remaining pours this week | Site engineer | 2026-07-02 | Done | 2026-07-01 |  | ✔ done
Handover documents | 6 days float, burning 2 an update | Start the O&M manuals now, not after commissioning |  | 2026-07-17 | Open |  | 17 | No owner: nobody will do it
Drainage connection to the outfall | 3 days float, lost 22 this update | Chase the discharge consent; ask for a conditional consent for the connection | Engineer | 2026-07-08 | Open |  | 8 | Open, on time
Temporary compound removal | 180 days float: linked only to the finish | Link it to the final account and the handover | Planner | 2026-07-03 | Open |  | 3 | Open, on time
Days to due count from the data date of the update in Setup.

## Updates
Updates | [10 empty] | The Project Control Hub
One line per update: the data date, the setting, the forecast finish and why it moved.
Add the line before you start the checklist. The finish movement and the health counts work themselves out.
Update | Data date | Same cut-off rule? | Scheduling option | Forecast finish | Days late vs contract | Moved since last update (days) | Health checks failing | Activities with negative float | Issued on | Working days to issue | Why the finish moved
1 | 2026-01-30 | Y | Progress override | 2026-07-24 | 0 |  | 6 | 0 | 2026-02-02 | 1 | First update. On programme.
2 | 2026-02-27 | Y | Progress override | 2026-07-24 | 0 | 0 | 6 | 0 | 2026-03-02 | 1 | South piling two days late; float absorbed it.
3 | 2026-03-31 | Y | Progress override | 2026-08-07 | 14 | 14 | 6 | 0 | 2026-04-02 | 2 | Rock at P17 and P18; the raft rebar at about 16 hours a tonne. Must-finish-on put on the substation slab.
4 | 2026-04-30 | N | Progress override | 2026-08-12 | 19 | 5 | 6 | 0 | 2026-05-08 | 6 | Cut-off moved to 6 May to "include the pour". Issued late.
5 | 2026-05-29 | Y | Progress override | 2026-08-14 | 21 | 2 | 6 | 0 | 2026-06-02 | 2 | Switchgear lead time still not confirmed in writing.
6 | 2026-06-30 | Y | Retained logic | 2026-09-04 | 42 | 21 | 6 | 2 |  |  | Switched to retained logic and took the must-finish-on off the substation slab: 21 days later. It stopped hiding.
7
8
9
10
11
12
The row with the teal border is the update in Setup. Days are calendar days; working days to issue count from the data date.
Formulas:
Working days to issue = IF(OR([Data date]="",[Issued on]=""),"",NETWORKDAYS([Data date],[Issued on])-1)

## Setup
Setup |  |  |  |  | The Project Control Hub
Which update this is, the contract date, and the limits the health check uses.
Change the update number every period, after you add its line in Updates. Everything else reads from here.
Project | Example project
This update (number) | 6 | The row in Updates that this checklist is for.
Data date (from Updates) | 2026-06-30 | Type it in Updates, on the row of this update.
Contract completion date | 2026-07-24 | The date the forecast finish is measured against.
Cut-off rule | Last working day of the month | Same day, same rules, every period (Topic 16).
Float this high is suspicious (days) | 100 | Pick a value well above any honest float on your job. Topic 17: 180 days on temporary works is a missing link.
Lags longer than this need an owner (days) | 10 | Curing can be a lag. An approval cannot.
Measure the float burn over (updates) | 3 | The slope is the average loss per update over this many updates.
Warn when float runs out within (updates) | 3 | Turns the Float trend amber before it turns red.
Scheduling software | Primavera P6
Working days since the last update | 22 | The Remaining days sheet uses it to see whether a finish moved.
LISTS · the drop-downs read from here
Status |  |  | Source of the figure | Owners (roles) | Scheduling option
Done |  |  | Site diary | Planner | Retained logic
Fixed |  |  | Inspection sheet | Project manager | Progress override
Open |  |  | Delivery note | Site manager | Actual dates
Not done |  |  | Survey | Site engineer
N/A |  |  | Timesheet | Engineer
|  |  | Test certificate | Design manager
|  |  | Phone call | Buyer
|  |  | Memory | Commercial
Piling sub
Concrete sub
Rebar sub
Groundworks
Electrical sub
Status: Done = checked, nothing wrong. Fixed = something was wrong and is now corrected. Open = found, not yet corrected. Not done = not checked yet. Must-do items need Done or Fixed before the update goes out.