## Start
Weekly progress report
A report that records the week, and a look-ahead that only holds work which is actually ready.
The Project Control Hub · free template
YOUR FRIDAY, IN SIX STEPS
1 | Setup → | Change the week number and the week ending date. | 1 minute
2 | Progress → | For each activity: actual %, remaining days and float from the updated schedule. Ask how many days are still needed, not how far along it is. | 15 minutes
3 | Look-ahead → | Construction lists the next two weeks. Mark the six tests Y or N. Anything not Ready moves to Constraints. | 15 minutes
4 | Constraints → | One row per failing test, with an owner and the date it is needed by. | 5 minutes
5 | Actions → | From the meeting: a person, a date, what done looks like. Close old ones with evidence. | 5 minutes
6 | Dashboard → | Write three lines: what changed, what is at risk, what decision is needed. Then copy this week’s numbers into History. | 5 minutes
Then read it in the meeting in this order: look-ahead first, while there is still time to clear a constraint; last week second, and only what changes something.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Green | Ready, on track, closed.
| Amber | Watch it: slipping, not ready, still open.
| Red | Late, overdue, or negative float. This is what the meeting is for.
WHAT IS IN THIS FILE
| Dashboard | One page: six numbers, four charts, the three lines, and what needs attention.
| Setup | The week, the date, and the team list for the drop-downs.
| Progress | Every activity: planned and actual %, remaining days, float, status and trend.
| S-curve | Cumulative planned against actual, week by week.
| Float trend | Float on the activities that matter, so the slope shows before the crisis does.
| Look-ahead | The next two weeks against the six readiness tests.
| Constraints | Blocked work, with an owner and a date, until it is closed.
| Actions | Actions from the meeting, with overdue days counted for you.
| History | One row a week, for the trend charts.
EXPLAINED IN
Reporting Topic 18 · The weekly report and the look-ahead
Reporting Topic 9 · Ready means six different things
Schedule Topic 16 · Schedule maintenance
Reporting Topic 23 · Minutes, actions and closure
Blank: every sheet ready to fill. The example file shows week 11 of the example project.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Weekly progress report | [7 empty] | The Project Control Hub
PROGRESS · ACTUAL | ACTIVITIES LATE |  | LOOK-AHEAD READY |  | REPEATS FROM LAST WEEK |  | OPEN CONSTRAINTS |  | ACTIONS OVERDUE
THIS WEEK IN THREE LINES |  |  | Exceptions only: what changed, what is now at risk, what decision is needed.
What changed
What is now at risk
Decision needed
PROGRESS AND FLOAT
READINESS AND TREND
NEEDS ATTENTION · late and watch activities, from Progress
Activity |  | Status | Float | Change | Slip (days) | Comment
Charts and tiles read from the other sheets. Write the three lines above; everything else updates by itself.

## Setup
Setup | The Project Control Hub
The week you are reporting, and the lists the other sheets use.
Change the week number and the week ending date every Friday. Everything else reads from here.
Project
Week number
Week ending
Prepared by
As at (for overdue counts) | Defaults to the week ending date. Type a date to override.
Week 1 ended on | Used to date the S-curve and History rows.
Team (used by the Owner drop-downs) | Areas (for your own sorting)
One name per row

## Progress
Progress | [19 empty] | The Project Control Hub
Every activity in the report: planned against actual, remaining days and float, this week against last.
Ask "how many days do you still need?", not "how far along are you?". Take float from the updated schedule.
ID | Activity | Area | Owner | Weight (%) | Baseline finish | Forecast finish | Slip (days) | Planned % to date | Actual % to date | Variance (pts) | Remaining days, last week | Remaining days, this week | Change (days) | Float last week | Float this week | Float change | Status | Trend | Comment | #
Weighted progress, whole report
Weights should add up to 100. Use value or budget share, not duration.
Late
Watch
On track
Complete

## S-curve
S-curve | [5 empty] | The Project Control Hub
Cumulative progress, planned against actual, week by week.
Planned comes from the baseline once. Each Friday add the actual figure from the Progress total.
Week | Week ending | Planned (cumulative) | Actual (cumulative) | Gap (pts) | This week, from the Progress sheet
1 |  |  |  |  | Planned
2 |  |  |  |  | Actual
3 |  |  |  |  | Type these into this week’s row.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Float trend
Float trend | The Project Control Hub
Total float on the activities that matter, week by week.
Read the slope, not the number. A line heading for zero is next month’s crisis, visible now.
Activity
The last two columns should match "Float last week" and "Float this week" on Progress.
Next week: copy columns C to I one place left, and type the new week in I.

## Look-ahead
Look-ahead · next two weeks | [18 empty] | The Project Control Hub
Prepared by construction, consolidated and challenged by project controls.
Answer all six tests with Y or N. Anything that is not Ready goes to the Constraints sheet, not into the plan.
ID | Activity | Area | Start | Finish | Crew | Drawing | Material | Plant | Labour | Permit | Access | Passed | Ready? | Blocked by | On last week’s list? | Weeks on the list | Note | This look-ahead
Items
Ready (all six tests)
Ready share
Repeats from last week
Repeat share
On the list 3 weeks or more
Which test stops work
Drawing
Material
Plant
Labour
Permit
Access
Mostly repeats means a list of blocked work, not a plan.

## Constraints
Constraint log | [9 empty] | The Project Control Hub
Blocked work lives here, where somebody has to close it.
One row per failing test. A constraint is closed with a date and the evidence, never by being forgotten.
ID | Activity | Failing test | Constraint | Owner | Raised | Needed by | Closed on | Days open | Status | Evidence of closure

## Actions
Actions | [9 empty] | The Project Control Hub
What the meeting decided: a person, a date, and what done looks like.
Close an action with a name, a date and the evidence. An action nobody can categorise was never an action.
No. | Raised in | Action | Owner | Due | What done looks like | Status | Days overdue | Closed by | Closed on | Evidence of closure
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## History
History | [7 empty] | The Project Control Hub
One row per week, so the Dashboard can show the trend.
Every Friday: copy the blue "This week" row and use Paste Special → Values into the next empty row.
This week (live)
Week | Week ending | Planned progress | Actual progress | Look-ahead ready | Repeats | Last week’s plan done | Open constraints | Overdue actions
Note on G6: Of last week’s look-ahead, the share that was actually done. Count it at the meeting.