## Start
Weekly progress report
A report that records the week, and a look-ahead that only holds work which is actually ready.
The Project Control Hub · free template · example: week 11 of the example project
YOUR FRIDAY, IN SIX STEPS
1 | Setup → | Change the week number and the week ending date. | 1 minute
2 | Progress → | For each activity: actual %, remaining days and float from the updated schedule. Ask how many days are still needed, not how far along it is. | 15 minutes
3 | Look-ahead → | Construction lists the next two weeks. Mark the six tests Y or N. Anything not Ready moves to Constraints. | 15 minutes
4 | Constraints → | One row per failing test, with an owner and the date it is needed by. | 5 minutes
5 | Actions → | From the meeting: a person, a date, what done looks like. Close old ones with evidence. | 5 minutes
6 | Dashboard → | Write three lines: what changed, what is at risk, what decision is needed. Then copy this week’s numbers into History. | 5 minutes
Then read it in the meeting in this order: look-ahead first, while there is still time to clear a constraint; last week second, and only what changes something.
HOW TO READ THE CELLS
| Yellow, blue text | Yours to fill in.
| White, black text | A formula. Leave it alone and it keeps working.
| Green | Ready, on track, closed.
| Amber | Watch it: slipping, not ready, still open.
| Red | Late, overdue, or negative float. This is what the meeting is for.
WHAT IS IN THIS FILE
| Dashboard | One page: six numbers, four charts, the three lines, and what needs attention.
| Setup | The week, the date, and the team list for the drop-downs.
| Progress | Every activity: planned and actual %, remaining days, float, status and trend.
| S-curve | Cumulative planned against actual, week by week.
| Float trend | Float on the activities that matter, so the slope shows before the crisis does.
| Look-ahead | The next two weeks against the six readiness tests.
| Constraints | Blocked work, with an owner and a date, until it is closed.
| Actions | Actions from the meeting, with overdue days counted for you.
| History | One row a week, for the trend charts.
EXPLAINED IN
Reporting Topic 18 · The weekly report and the look-ahead
Reporting Topic 9 · Ready means six different things
Schedule Topic 16 · Schedule maintenance
Reporting Topic 23 · Minutes, actions and closure
Example: week 11 of the example project, during the piling. The events, owners and figures named in the lessons (the rock at P17, the rebar gang at 16 hours a tonne, the wayleave letter, the boreholes) are the example project’s. Quantities, dates, weights and the week-by-week history are illustrative.
Free to use and adapt on your own projects. https://theprojectcontrolhub.com/

## Dashboard
Weekly progress report | [7 empty] | The Project Control Hub
Example project · Week 11 · week ending 13 Mar 2026 · Project controls
PROGRESS · ACTUAL | ACTIVITIES LATE |  | LOOK-AHEAD READY |  | REPEATS FROM LAST WEEK |  | OPEN CONSTRAINTS |  | ACTIONS OVERDUE
38.24% | 3 |  | 5 |  | 45.45% |  | 9 |  | 2
planned 47% · -9 pts | negative float · 5 to watch |  | of 11 items · 45% |  | mostly new work: a plan |  | 1 overdue |  | of 8 open actions
THIS WEEK IN THREE LINES |  |  | Exceptions only: what changed, what is now at risk, what decision is needed.
What changed | Rock in the north pile bores at P17 and P18. The north piling now needs 15 days, not 12, and its float is negative: it, the north pile caps and the access road are late.
What is now at risk | The raft. The rebar gang is taking about 16 hours a tonne against 8 in the estimate, and the bar schedule revision for bay 2 is overdue.
Decision needed | Approve two boreholes in the north half ($6,800) before the rig moves on. Serve the Notice of Claim for the rock by 31 March.
PROGRESS AND FLOAT
READINESS AND TREND
NEEDS ATTENTION · late and watch activities, from Progress
Activity |  | Status | Float | Change | Slip (days) | Comment
Bored piles, north half |  | Late | -2 | -6 | 7 | Rock at P17 and P18 on 3 Mar. Two boreholes proposed ($6,800).
Pile caps, south |  | Watch | 5 | -1 | 5 | Last two caps waiting on cube results.
Pile caps, north |  | Late | -2 | -6 | 7 | Follows the north piling.
Ground beams |  | Watch | 6 | -2 | 4 | Steel for GB4 to GB6 on site.
Raft reinforcement |  | Watch | 6 | -4 | 14 | About 16 hours a tonne against 8 in the estimate.
Raft concrete pours |  | Watch | 6 | -4 | 12 | Follows raft reinforcement.
Switchgear procurement (long lead) |  | Watch | 9 | -6 | 14 | Lead time not yet confirmed in writing.
Wayleave and access road |  | Late | -1 | -3 | 14 | Wayleave letter due 14 Mar (Ahmet).
Charts and tiles read from the other sheets. Write the three lines above; everything else updates by itself.

## Setup
Setup |  | The Project Control Hub
The week you are reporting, and the lists the other sheets use.
Change the week number and the week ending date every Friday. Everything else reads from here.
Project | Example project
Week number | 11
Week ending | 2026-03-13
Prepared by | Project controls
As at (for overdue counts) | 2026-03-13 | Defaults to the week ending date. Type a date to override.
Week 1 ended on | 2026-01-02 | Used to date the S-curve and History rows.
Team (used by the Owner drop-downs) |  | Areas (for your own sorting)
One name per row | Project manager | Site
| Site manager | South
| Site engineer | North
| Engineer | Substation
| Design manager | Procurement
Planner
Buyer
Commercial
Ahmet
Piling sub
Concrete sub
Rebar sub
Groundworks

## Progress
Progress | [19 empty] | The Project Control Hub
Every activity in the report: planned against actual, remaining days and float, this week against last.
Ask "how many days do you still need?", not "how far along are you?". Take float from the updated schedule.
ID | Activity | Area | Owner | Weight (%) | Baseline finish | Forecast finish | Slip (days) | Planned % to date | Actual % to date | Variance (pts) | Remaining days, last week | Remaining days, this week | Change (days) | Float last week | Float this week | Float change | Status | Trend | Comment | #
A01 | Mobilisation and site set-up | Site | Site manager | 4 | 2026-01-09 | 2026-01-09 | 0 | 100% | 100% | 0 | 0 | 0 | 0 |  |  |  | Complete
A02 | Site clearance and setting out | Site | Site engineer | 3 | 2026-01-23 | 2026-01-21 | -2 | 100% | 100% | 0 | 0 | 0 | 0 |  |  |  | Complete
A03 | Bored piles, south half | South | Piling sub | 8 | 2026-02-20 | 2026-02-24 | 4 | 100% | 100% | 0 | 0 | 0 | 0 |  |  |  | Complete |  | Finished two working days late.
A04 | Bored piles, north half | North | Piling sub | 8 | 2026-03-20 | 2026-03-27 | 7 | 80% | 55% | -25 | 12 | 15 | 3 | 4 | -2 | -6 | Late | ▼ float down 6 | Rock at P17 and P18 on 3 Mar. Two boreholes proposed ($6,800). | 1
A05 | Pile caps, south | South | Concrete sub | 5 | 2026-03-06 | 2026-03-11 | 5 | 100% | 90% | -10 | 3 | 2 | -1 | 6 | 5 | -1 | Watch | ▼ float down 1 | Last two caps waiting on cube results. | 2
A06 | Pile caps, north | North | Concrete sub | 5 | 2026-04-03 | 2026-04-10 | 7 | 10% | 0% | -10 | 20 | 23 | 3 | 4 | -2 | -6 | Late | ▼ float down 6 | Follows the north piling. | 3
A07 | Ground beams | South | Concrete sub | 6 | 2026-03-27 | 2026-03-31 | 4 | 30% | 20% | -10 | 12 | 13 | 1 | 8 | 6 | -2 | Watch | ▼ float down 2 | Steel for GB4 to GB6 on site. | 4
A08 | Raft blinding and waterproofing | Substation | Groundworks | 4 | 2026-03-20 | 2026-03-20 | 0 | 50% | 45% | -5 | 5 | 4 | -1 | 10 | 10 | 0 | On track | ● steady
A09 | Raft reinforcement | Substation | Rebar sub | 8 | 2026-04-10 | 2026-04-24 | 14 | 35% | 18% | -17 | 18 | 22 | 4 | 10 | 6 | -4 | Watch | ▼ float down 4 | About 16 hours a tonne against 8 in the estimate. | 5
A10 | Raft concrete pours | Substation | Concrete sub | 10 | 2026-04-24 | 2026-05-06 | 12 | 0% | 0% | 0 | 10 | 10 | 0 | 10 | 6 | -4 | Watch | ▼ float down 4 | Follows raft reinforcement. | 6
A11 | Substation slab | Substation | Concrete sub | 10 | 2026-05-08 | 2026-05-08 | 0 | 0% | 0% | 0 | 30 | 30 | 0 | 18 | 18 | 0 | On track | ● steady
A12 | Drainage and ducts | Site | Groundworks | 9 | 2026-04-17 | 2026-04-17 | 0 | 25% | 30% | 5 | 20 | 18 | -2 | 12 | 14 | 2 | On track | ▲ float up 2 | Gang moved from the north; ahead.
A13 | Switchgear procurement (long lead) | Procurement | Buyer | 14 | 2026-06-05 | 2026-06-19 | 14 | 40% | 30% | -10 | 70 | 70 | 0 | 15 | 9 | -6 | Watch | ▼ float down 6 | Lead time not yet confirmed in writing. | 7
A14 | Wayleave and access road | Site | Ahmet | 6 | 2026-03-13 | 2026-03-27 | 14 | 100% | 50% | -50 | 5 | 10 | 5 | 2 | -1 | -3 | Late | ▼ float down 3 | Wayleave letter due 14 Mar (Ahmet). | 8
| Weighted progress, whole report |  |  | 100 |  |  |  | 47.35% | 38.24% | -9.11
Weights should add up to 100. Use value or budget share, not duration.
| Late |  |  | 3
| Watch |  |  | 5
| On track |  |  | 3
| Complete |  |  | 3

## S-curve
S-curve | [5 empty] | The Project Control Hub
Cumulative progress, planned against actual, week by week.
Planned comes from the baseline once. Each Friday add the actual figure from the Progress total.
Week | Week ending | Planned (cumulative) | Actual (cumulative) | Gap (pts) | This week, from the Progress sheet
1 | 2026-01-02 | 1% | 1% | 0 | Planned | 47.35%
2 | 2026-01-09 | 2.5% | 2.3% | 0 | Actual | 38.24%
3 | 2026-01-16 | 4.5% | 4.2% | 0 | Type these into this week’s row.
4 | 2026-01-23 | 7% | 6.5% | -1
5 | 2026-01-30 | 10% | 9.3% | -1
6 | 2026-02-06 | 14% | 12.8% | -1
7 | 2026-02-13 | 19% | 17% | -2
8 | 2026-02-20 | 25% | 21.8% | -3
9 | 2026-02-27 | 31.5% | 26.9% | -5
10 | 2026-03-06 | 39% | 32.4% | -7
11 | 2026-03-13 | 47.35% | 38.24% | -9
12 | 2026-03-20 | 55%
13 | 2026-03-27 | 62%
14 | 2026-04-03 | 68%
15 | 2026-04-10 | 73.5%
16 | 2026-04-17 | 78%
17 | 2026-04-24 | 82%
18 | 2026-05-01 | 85.5%
19 | 2026-05-08 | 88.5%
20 | 2026-05-15 | 91%
21 | 2026-05-22 | 93%
22 | 2026-05-29 | 94.6%
23 | 2026-06-05 | 96%
24 | 2026-06-12 | 97.1%
25 | 2026-06-19 | 98%
26 | 2026-06-26 | 98.7%
27 | 2026-07-03 | 99.2%
28 | 2026-07-10 | 99.6%
29 | 2026-07-17 | 99.85%
30 | 2026-07-24 | 100%
31 | 2026-07-31
32 | 2026-08-07
33 | 2026-08-14
34 | 2026-08-21
35 | 2026-08-28
36 | 2026-09-04
37 | 2026-09-11
38 | 2026-09-18
39 | 2026-09-25
40 | 2026-10-02
Formulas:
Week ending = IF(Setup!$B11="","",Setup!$B11+7*([Week]-1))

## Float trend
Float trend | [8 empty] | The Project Control Hub
Total float on the activities that matter, week by week.
Read the slope, not the number. A line heading for zero is next month’s crisis, visible now.
Activity | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Bored piles, north half | 10 | 9 | 9 | 8 | 7 | 6 | 4 | -2
Pile caps, north | 10 | 9 | 9 | 8 | 7 | 6 | 4 | -2
Ground beams | 12 | 11 | 10 | 10 | 9 | 8 | 8 | 6
Raft reinforcement | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 6
Switchgear procurement | 24 | 22 | 20 | 18 | 17 | 15 | 15 | 9
Wayleave and access road | 9 | 8 | 6 | 5 | 4 | 3 | 2 | -1
The last two columns should match "Float last week" and "Float this week" on Progress.
Next week: copy columns C to I one place left, and type the new week in I.

## Look-ahead
Look-ahead · next two weeks | [18 empty] | The Project Control Hub
Prepared by construction, consolidated and challenged by project controls.
Answer all six tests with Y or N. Anything that is not Ready goes to the Constraints sheet, not into the plan.
ID | Activity | Area | Start | Finish | Crew | Drawing | Material | Plant | Labour | Permit | Access | Passed | Ready? | Blocked by | On last week’s list? | Weeks on the list | Note | This look-ahead
L01 | Bored piles P18 to P24 | North | 2026-03-16 | 2026-03-20 | Piling sub | Y | Y | Y | Y | Y | Y | 6 / 6 | Ready | — | Y | 2 | Rig back in service 9 Mar. | Items | 11
L02 | Pile caps PC1 to PC3 | North | 2026-03-17 | 2026-03-19 | Concrete sub | Y | Y | N | Y | Y | N | 4 / 6 | Not ready | Plant, Access | Y | 3 | Crane and sign-off. | Ready (all six tests) | 5
L03 | Raft rebar, bay 2 | Substation | 2026-03-16 | 2026-03-20 | Rebar sub | N | Y | Y | Y | Y | Y | 5 / 6 | Not ready | Drawing | Y | 2 | Bar schedule revision. | Ready share | 45.45%
L04 | Blinding, substation slab | Substation | 2026-03-19 | 2026-03-19 | Groundworks | Y | Y | Y | Y | Y | Y | 6 / 6 | Ready | — | N | 1 |  | Repeats from last week | 5
L05 | Ground beams GB4 to GB6 | South | 2026-03-16 | 2026-03-20 | Concrete sub | Y | Y | Y | Y | Y | Y | 6 / 6 | Ready | — | Y | 2 |  | Repeat share | 45.45%
L06 | Drainage run D3 to D5 | Site | 2026-03-16 | 2026-03-18 | Groundworks | Y | Y | Y | Y | Y | Y | 6 / 6 | Ready | — | N | 1 |  | On the list 3 weeks or more | 2
L07 | Raft waterproofing, bay 1 | Substation | 2026-03-18 | 2026-03-20 | Groundworks | Y | N | Y | Y | Y | Y | 5 / 6 | Not ready | Material | N | 1 | Membrane delivery.
L08 | Access road sub-base | Site | 2026-03-23 | 2026-03-27 | Groundworks | Y | Y | Y | Y | N | N | 4 / 6 | Not ready | Permit, Access | Y | 4 | Waits for the wayleave. | Which test stops work
L09 | Cable ducts to substation | Substation | 2026-03-23 | 2026-03-25 | Groundworks | Y | Y | Y | N | Y | Y | 5 / 6 | Not ready | Labour | N | 1 | Duct gang on drainage. | Drawing | 2
L10 | Pile caps PC4 to PC6, south | South | 2026-03-23 | 2026-03-25 | Concrete sub | Y | Y | Y | Y | Y | Y | 6 / 6 | Ready | — | N | 1 |  | Material | 1
L11 | Raft rebar, bay 3 | Substation | 2026-03-23 | 2026-03-27 | Rebar sub | N | Y | Y | N | Y | Y | 4 / 6 | Not ready | Drawing, Labour | N | 1 |  | Plant | 1
[18 empty] | Labour | 2
[18 empty] | Permit | 1
[18 empty] | Access | 2
Mostly repeats means a list of blocked work, not a plan.

## Constraints
Constraint log | [9 empty] | The Project Control Hub
Blocked work lives here, where somebody has to close it.
One row per failing test. A constraint is closed with a date and the evidence, never by being forgotten.
ID | Activity | Failing test | Constraint | Owner | Raised | Needed by | Closed on | Days open | Status | Evidence of closure
C01 | Pile caps PC1 to PC3 | Plant | Crane booked to another zone on 17 Mar | Site manager | 2026-03-06 | 2026-03-16 |  | 7 | Open
C02 | Pile caps PC1 to PC3 | Access | Piles not signed off: inspection request not raised | Engineer | 2026-03-06 | 2026-03-16 |  | 7 | Open
C03 | Raft rebar, bay 2 | Drawing | Bar schedule revision not issued for construction | Design manager | 2026-03-04 | 2026-03-12 |  | 9 | Overdue
C04 | Raft waterproofing, bay 1 | Material | Membrane delivery date not confirmed | Buyer | 2026-03-11 | 2026-03-16 |  | 2 | Open
C05 | Access road sub-base | Permit | Wayleave not confirmed: letter to be issued | Ahmet | 2026-02-20 | 2026-03-14 |  | 21 | Open
C06 | Access road sub-base | Access | Haul route crosses third-party land until the wayleave | Commercial | 2026-02-20 | 2026-03-14 |  | 21 | Open
C07 | Cable ducts to substation | Labour | Duct gang moved to drainage | Site manager | 2026-03-11 | 2026-03-16 |  | 2 | Open
C08 | Raft rebar, bay 3 | Drawing | Same bar schedule revision as bay 2 | Design manager | 2026-03-11 | 2026-03-20 |  | 2 | Open
C09 | Raft rebar, bay 3 | Labour | Rebar gang fully on bay 2 | Site manager | 2026-03-11 | 2026-03-23 |  | 2 | Open
C10 | Bored piles P18 to P24 | Plant | Rig repair after the rock | Piling sub | 2026-03-04 | 2026-03-09 | 2026-03-09 | 5 | Closed | Rig back in service, daily report 9 Mar

## Actions
Actions | [9 empty] | The Project Control Hub
What the meeting decided: a person, a date, and what done looks like.
Close an action with a name, a date and the evidence. An action nobody can categorise was never an action.
No. | Raised in | Action | Owner | Due | What done looks like | Status | Days overdue | Closed by | Closed on | Evidence of closure
1 | Weekly meeting, 6 Mar | Issue the wayleave letter | Ahmet | 2026-03-14 | Letter sent to the stated address, receipt on file | Open
2 | Weekly meeting, 6 Mar | Approve two boreholes in the north half ($6,800) | Project manager | 2026-03-13 | Instruction issued to the drilling contractor | Open
3 | Weekly meeting, 6 Mar | Drill two boreholes in the north half | Engineer | 2026-03-20 | Two logs filed against the pile layout | Open
4 | Weekly meeting, 6 Mar | Run a credit check on the steel supplier | Buyer | 2026-03-13 | Report on file and read | Closed |  | Buyer | 2026-03-12 | Report filed in the supplier folder
5 | Weekly meeting, 6 Mar | Confirm the switchgear lead time in writing | Buyer | 2026-03-11 | Supplier’s written date on file | Open | 2
6 | Weekly meeting, 6 Mar | Send the pre-application enquiry for the discharge consent | Engineer | 2026-03-20 | Enquiry acknowledged by the authority | Open
7 | Weekly meeting, 6 Mar | Issue the bar schedule revision for raft bay 2 | Design manager | 2026-03-12 | Revision issued for construction | Open | 1
8 | Weekly meeting, 13 Mar | Raise the inspection request for piles under PC1 to PC3 | Engineer | 2026-03-13 | Request logged with the resident engineer | Open
9 | Weekly meeting, 13 Mar | Serve the Notice of Claim for the rock at P17 | Commercial | 2026-03-31 | Notice identified as a Notice, sent to the stated address | Open
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## History
History | [7 empty] | The Project Control Hub
One row per week, so the Dashboard can show the trend.
Every Friday: copy the blue "This week" row and use Paste Special → Values into the next empty row.
This week (live)
11 | 2026-03-13 | 47.35% | 38.24% | 45.45% | 45.45% | 52% | 9 | 2
Week | Week ending | Planned progress | Actual progress | Look-ahead ready | Repeats | Last week’s plan done | Open constraints | Overdue actions
6 | 2026-02-06 | 14% | 12.8% | 80% | 20% | 85% | 3 | 0
7 | 2026-02-13 | 19% | 17% | 75% | 25% | 80% | 4 | 0
8 | 2026-02-20 | 25% | 21.8% | 70% | 30% | 72% | 4 | 1
9 | 2026-02-27 | 31.5% | 26.9% | 64% | 36% | 70% | 5 | 1
10 | 2026-03-06 | 39% | 32.4% | 55% | 40% | 58% | 7 | 1
11 | 2026-03-13 | 47.35% | 38.24% | 45.45% | 45.45% | 52% | 9 | 2
Note on G6: Of last week’s look-ahead, the share that was actually done. Count it at the meeting.